## Form 7 - DFU
FDP Form 7 - 20% COMPONENT OF THE IRA UTILIZATION
UTILIZATION OF THE 20% OF THE NATIONAL TAX ALLOTMENT
| REGION: |  | MIMAROPA |  |  | CALENDAR YEAR: | 2024
| PROVINCE: |  | PALAWAN |  |  | QUARTER: | 2
| CITY/MUNICIPALITY: |  | CITY OF PUERTO PRINCESA
Code | Program / Project |  |  |  | Location | Total Cost | Date Started | Target Completion | Project Status |  | No. of Extension, if any | Remarks
[9 empty] | % of | Total Cost
[9 empty] | Completion | Incurred to Date
ECONOMIC DEVELOPMENT
8918-3(23) | Completion of Kamuning Public Market Site Development (Road, Parking, Sidewalk, and Drainage)
| 3.0 Capital Outlay | [10 empty] | Project on-going
|  | Other Land Improvements |  |  | Kamuning | 26628000 | 2024-02-22 | 2024-08-19 | 51.1% | 9342113.15 |  | By contract
8918-4(23) | Site Development of Baywalk Public Market (Road, Parking, Sidewalk and Drainage)
| 3.0 Capital Outlay | [10 empty] | Project on-going
|  | Other Land Improvements |  |  | Matahimik | 34367000 | 2024-02-22 | 2024-11-02 | 37.56% | 5086896.28 |  | By contract
8918-5(23) | Completion of Macarascas Mini City Hall Perimeter Fence
| 3.0 Capital Outlay | [10 empty] | Project on-going
|  | Other Land Improvements |  |  | Macarascas | 3462221 | 2024-02-22 | 2024-05-21 | 89.02% | 57500 |  | By contract
8918-6(23) | Completion of Irawan Agri-Trading Center Fence
| 3.0 Capital Outlay | [10 empty] | Project on-going
|  | Other Land Improvements |  |  | Irawan | 6975000 | 2024-02-22 | 2024-07-20 | 47.97% | 3343743.29 |  | By contract
Site Development of Napsan Mini City Hall ( Road, Parking, Sidewalk and Drainage)
8918-8(23) | 3.0 Capital Outlay | [10 empty] | No movement due
|  | Other Land Improvements |  |  | Napsan | 12453000 | 2024-02-22 | 2024-07-20 | 1.42% | 1816832.35 |  | to land dispute
Site Development of Macarascas Mini City Hall ( Road, Parking, Sidewalk and Drainage)
| 3.0 Capital Outlay | [10 empty] | Project on-going
8918-9(23) |  | Other Land Improvements |  |  | Macarascas | 15000000 | 2024-02-22 | 2024-09-03 | 44.15% | 2250029.44 |  | By contract
Site Development of Salvacion Public Market (Road, Parking, Sidewalk and Drainage)
| 3.0 Capital Outlay | [10 empty] | Project on-going
8918-10(23) |  | Other Land Improvements |  |  | Salvacion | 20000000 | 2024-02-22 | 2024-09-18 | 97.6% | 18020988.67 |  | By contract
Construction of Kamuning Public Market Perimeter Fence and Landscape
| 3.0 Capital Outlay | [10 empty] | Project on-going
8918-11(23) |  | Other Land Improvements |  |  | Kamuning | 6069520 | 2024-02-22 | 2024-07-20 | 43.8% |  |  | By contract
Construction of New City Cemetery Phase V
3.0 Capital Outlay
8918-13(23) |  | Other Land Improvements |  |  | Sta. Lourdes | 30000000 | [5 empty] | For implementation
Construction of New Muslim Cemetery Perimeter Fence, Brgy. San Jose
| 3.0 Capital Outlay | [10 empty] | Project on-going
8918-14(23) |  | Other Land Improvements |  |  | San Jose | 2334700 | 2024-04-29 | 2024-08-11 | 65.6% | 1416185.3 |  | By admin
Concreting of Road Leading to Balsahan River, Brgy. Iwahig
3.0 Capital Outlay
8918-15(23) |  | Infrastructure Assets - Road Networks |  |  | Iwahig | 13500000 | [5 empty] | For implementation
Concreting of Access Road to Ubaldo Conde High School, Brgy. Manalo
| 3.0 Capital Outlay | [10 empty] | For implementation
8918-16(23) |  | Infrastructure Assets - Road Networks |  |  | Manalo | 3835000 |  |  |  | 3555787.1 |  | By admin
Replacemet/Concreting of Manalo Extension (Fernandez to Abrea Road) Phase II, Brgy. Milagrosa
| 3.0 Capital Outlay | [10 empty] | Project on-going
8918-17(23) |  | Infrastructure Assets - Road Networks |  |  | Milagrosa | 46067000 | 2024-02-22 | 2024-09-18 | 21.68% | 148600 |  | By contract
Concreting/Completion of Cactus Road with Drainage System, Brgy. Sta. Monica
| 3.0 Capital Outlay | [10 empty] | Project on-going
8918-18(23) |  | Infrastructure Assets - Road Networks |  |  | Sta. Monica | 5539000 | 2024-04-29 | 2024-10-10 | 25.99% | 809980.22 |  | By contract
Concreting/Completion of Perimeter Road at Magbanua Elementary School, Brgy. San Pedro
| 3.0 Capital Outlay | [10 empty] | For implementation
8918-19(23) |  | Infrastructure Assets - Road Networks |  |  | San Pedro | 2992000 |  |  |  | 2502346.15 |  | By admin
Concreting of Caramuran Extension at Purok El Rancho, Brgy. Sta. Monica
| 3.0 Capital Outlay | [10 empty] | Project on-going
8918-22(23) |  | Infrastructure Assets - Road Networks |  |  | Sta. Monica | 7532000 | 2024-02-22 | 2024-05-06 | 64.78% |  |  | By contract
Concreting of Road Networks at Medina Relocation Site, Brgy. Sicsican
| 3.0 Capital Outlay | [10 empty] | Project on-going
8918-23(23) |  | Infrastructure Assets - Road Networks |  |  | Sicsican | 10000000 | 2024-02-22 | 2024-07-05 | 93.44% | 5171484.61 |  | By contract
Concreting of Arcinas Road with Drainage System beside Provincial PNP Station, Brgy. Tiniguiban
| 3.0 Capital Outlay | [10 empty] | Project on-going
8918-24(23) |  | Infrastructure Assets - Road Networks |  |  | Tiniguiban | 13691000 | 2024-02-22 | 2024-11-17 | 85.31% | 9459010.09 |  | By contract
| Concreting of Road Network at Engineering/Architecture Building and GSO Warehouse | [10 empty] | Project suspended due to various materials & equipments obstructing the proposed road way
3.0 Capital Outlay
8918-25(23) |  | Infrastructure Assets - Road Networks |  |  | Sta. Monica | 24000000 | 2024-02-22 | 2024-09-18 | 6% | 3649391.86
Concreting of Laban-Buesa Road (Interior Casuy Road), Brgy. Sta. Monica
| 3.0 Capital Outlay | [10 empty] | For implementation
8918-26(23) |  | Infrastructure Assets - Road Networks |  |  | Sta. Monica | 3150000 |  |  |  | 2343170.15 |  | By admin
Concreting of Felimon Lagan Road (Interior Hagedorn-Libis Road), Brgy. San Pedro
| 3.0 Capital Outlay | [10 empty] | Project on-going
8918-30(23) |  | Infrastructure Assets - Road Networks |  |  | San Pedro | 9884000 | 2024-02-22 | 2024-10-03 | 72.76% | 8780141.88 |  | By contract
Concreting of VISAPA Road 1 with Drainage Syatem, Brgy. Irawan
| 3.0 Capital Outlay | [10 empty] | Project on-going
8918-32-a(23) |  | Infrastructure Assets - Road Networks |  |  | Irawan | 10000000 | 2024-02-29 | 2024-07-27 | 54.86% | 103200 |  | By contract
Road Reblocking of Paduga Road (National Highway to Sampaloc Street, Brgy. Sta. Monica)
| 3.0 Capital Outlay | [10 empty] | Project on-going
8918-32-b(23) |  | Infrastructure Assets - Road Networks |  |  | Sta. Monica | 10764000 | 2024-06-26 | 2024-11-07 | 47% | 9905170.84 |  | By admin
Road Reblocking of Salve Regina Road, Brgy. Tiniguiban
| 3.0 Capital Outlay | [10 empty] | For implementation
8918-32-c(23) |  | Infrastructure Assets - Road Networks |  |  | Tiniguiban | 261500 |  |  |  | 204269.7 |  | By admin
Road Reblocking of Parangue Road, Brgy. Sicsican
| 3.0 Capital Outlay | [10 empty] | For implementation
8918-32-d(23) |  | Infrastructure Assets - Road Networks |  |  | Sicsican | 813500 |  |  |  | 721308.35 |  | By admin
Road Reblocking of Manalo Street (H. Mendoza Street to Fernandez Street)
| 3.0 Capital Outlay | [10 empty] | For implementation
8918-32-e(23) |  | Infrastructure Assets - Road Networks |  |  | Various Brgys. | 9996500 |  |  |  | 9193365.72 |  | By admin
Asphalt Overlay of Burgos Street, Various Barangays
| 3.0 Capital Outlay | [10 empty] | Project on-going
8918-32-f(23) |  | Infrastructure Assets - Road Networks |  |  | Various Brgys. | 9265000 | 2024-06-13 | 2024-07-11 | 47.92% | 8966594.85 |  | By admin
Asphalt Overlay of H. Mendoza Street
| 3.0 Capital Outlay | [10 empty] | Project Completed
8918-33-a(23) |  | Infrastructure Assets - Road Networks |  |  | Various Brgys. | 10066500 | 2024-04-22 | 2024-06-11 | 100% | 10018154.76 |  | By admin
Asphalt Overlay of Palanca Road
| 3.0 Capital Outlay | [10 empty] | For implementation
8918-33-b(23) |  | Infrastructure Assets - Road Networks |  |  | Various Brgys. | 1899000 |  |  |  | 1826069.44 |  | By admin
Asphalt Overlay of E. Valencia Street
| 3.0 Capital Outlay | [10 empty] | For implementation
8918-33-c(23) |  | Infrastructure Assets - Road Networks |  |  | Various Brgys. | 9536500 |  |  |  | 9437808.43 |  | By admin
Asphalt Overlay of City PNP Entrance
| 3.0 Capital Outlay | [10 empty] | Project on-going
|  | Infrastructure Assets - Road Networks |  |  | San Pedro | 1664000 | 2024-07-30 | 2024-08-13 |  | 1567624.05 |  | By admin
8918-33-d(23) | Concreting of Katarungan Road (Runway to Baltan Catholic Church)
| 3.0 Capital Outlay | [10 empty] | For implementation
|  | Infrastructure Assets - Road Networks |  |  | Various Brgys. | 3470100 |  |  |  | 2744875.3 |  | By admin
8918-33-e(23) | Concreting of Access Road to Martha Ville Sibdivision, Brgy. Irawan
| 3.0 Capital Outlay | [10 empty] | Project on-going
|  | Infrastructure Assets - Road Networks |  |  | Irawan | 10000000 | 2024-02-22 | 2024-05-05 | 81.14% | 1483791.89 |  | By contract
8918-33-f(23) | Concreting of San Juan Road (Libis Road to Kalikasan Homes), Brgy. San Pedro
| 3.0 Capital Outlay | [10 empty] | Project on-going
|  | Infrastructure Assets - Road Networks |  |  | San Pedro | 7406500 | 2024-02-22 | 2024-06-05 | 98.69% | 6667054.77 |  | By contract
8918-33-g(23) | 10% PRDP Counterpart - FMR Town Site, Macarascas to Purok Cabairan, Brgy. Manalo
3.0 Capital Outlay
|  | Infrastructure Assets - Road Networks |  |  | Manalo | 20000000 | [5 empty] | For implementation
8918-33-h(23) | Concreting of Farm-to-Market Road Leading to Bisor Phase II, Brgy. Bacungan
| 3.0 Capital Outlay | [10 empty] | Project on-going
|  | Infrastructure Assets - Road Networks |  |  | Bacungan | 5000000 | 2024-02-22 | 2024-07-20 | 94.5% | 103200 |  | By contract
8918-7(23) | Concreting/Completion of FMR from Purok Anonang to Purok Star Apple (Verosel), Brgy. Sicsican
| 3.0 Capital Outlay | [10 empty] | Project on-going
|  | Infrastructure Assets - Road Networks |  |  | Sicsican | 27369000 | 2024-02-20 | 2024-10-10 | 53.67% | 13257157.56 |  | By contract
8918-12(23) | Concreting of Farm-to-Market Road Phase II, Brgy. Marufinas
| 3.0 Capital Outlay | [10 empty] | Project on-going
|  | Infrastructure Assets - Road Networks |  |  | Marufinas | 10000000 | 2024-06-25 | 2024-11-21 | 33.68% |  |  | By contract
Concreting of Puting Buhangin Farm-to-Market Road, Brgy. Mangingisda
8918-31(23) | 3.0 Capital Outlay | [10 empty] | Project on-going
|  | Infrastructure Assets - Road Networks |  |  | Mangingisda | 10000000 | 2024-02-22 | 2024-07-05 | 99.87% | 6377445.78 |  | By contract
Construction of Hanging Bridge at Purok 5, Brgy. Inagawan-Sub Colony
8918-20(23) | 3.0 Capital Outlay
|  | Infrastructure Assets - Road Networks |  |  | Inagawan-Sub | 9250000 | [5 empty] | Unimplemented
Construction of Hanging Bridge at No. 2 at Sitio Tagnaya
8918-21(23) | 3.0 Capital Outlay | [10 empty] | Project on-going
|  | Infrastructure Assets - Road Networks |  |  | Concepcion | 15500000 | 2024-02-22 | 2025-01-16 | 40.23% |  |  | By contract
Completion of Busngol RC Box Culvert ( Concreting of Approach and Slope Protection), Brgy. Sta. Lourdes
8918-28(23) | 3.0 Capital Outlay | [10 empty] | Project on-going
|  | Infrastructure Assets - Road Networks |  |  | Sta. Lourdes | 7532500 | 2024-02-22 | 2024-08-19 | 73.77% | 1153865.55 |  | By contract
Completion of Sidewalk and Slope Protection at Balayong People's Park
8918-29(23) | 3.0 Capital Outlay
|  | Infrastructure Assets - Road Networks |  |  | Sta. Monica | 7044000 | 2024-02-22 | 2024-05-06 | 100% | 5762526.55 |  | Project Completed
Completion of Sidewalk , Curb and Gutter at Suha Road. Brgy. San Jose
8918-27(23) | 3.0 Capital Outlay | [10 empty] | For implementation
|  | Infrastructure Assets - Road Networks |  |  | San Jose | 3247500 |  |  |  | 2017409.01 |  | By admin
Construction of Loading and Unloading Bay along Manalo Street (PNS, PSU-LES, and PP Pilot ES)
| 3.0 Capital Outlay | [10 empty] | Project on-going
|  | Infrastructure Assets - Road Networks |  |  | Various Brgys. | 4780000 | 2024-03-02 | 2024-06-29 | 100% | 730811.25 |  | By contract
8918-1(23)
Construction of Slope Protection at Maoyon Bridge, Brgy. Maoyon
3.0 Capital Outlay
|  | Infrastructure Assets - Road Networks |  |  | Maoyon | 5000000 | 2024-03-02 | 2024-06-20 | 100% | 2591478.47 |  | Project Completed
8918-2(23)
Rehabilitation of Water Supply System, Brgy. Bagong Bayan
| 3.0 Capital Outlay | [10 empty] | Project on-going
|  | Water Supply System |  |  | Bagong Bayan | 5000000 |  |  | 18.83% | 3230330.21 |  | By admin
Development of Level III Water System in Barangay Maoyon and Manalo
| 3.0 Capital Outlay | [10 empty] | MOA with PPCWD
|  | Water Supply System |  |  | Various Brgys. | 4000000 | [5 empty] | Unimplemented
Rehabilitation/Improvement of Plaza Quartel (Fence, Gate, Landscape, Public Toilet, Admin Office, Information, Monument and Amphitheater with Stage), Brgy. Liwanag
| 3.0 Capital Outlay | [10 empty] | Project on-going
|  | Parks, Plazas and Monuments |  |  | Liwanag | 15979402 | 2024-04-15 | 2024-09-11 | 20.79% |  |  | By contract
Construction of Two-Storey PNP Building , Brgy. Luzviminda
| 3.0 Capital Outlay | [10 empty] | Project on-going
|  | Buildings |  |  | Luzviminda | 25194858 | 2024-04-08 | 2025-01-02 | 16.28% | 3673200 |  | By contract
Renovation of Old Terminal Building - Offices, Brgy. San Jose
| 3.0 Capital Outlay | [10 empty] | Project on-going
|  | Buildings |  |  | San Jose | 58473159.94 | 2024-05-03 | 2025-02-16 | 1.78% |  |  | By contract
Completion of City Engineering and Architecture Building ( Fixture, Office Furniture)
| 3.0 Capital Outlay | [10 empty] | Project awarded
|  | Buildings |  |  | Sta. Monica | 49618597 | [5 empty] | By contract
Construction of Standard Day Care Center, Brgy. Kamuning
| 3.0 Capital Outlay | [10 empty] | Project on-going
|  | School Buildings |  |  | Kamuning | 5779474 | 2024-02-22 | 2024-07-20 | 49.85% | 879551.12 |  | By contract
Construction of Standard Day Care Center, Purok Manturon, Brgy. Cabayuygan
| 3.0 Capital Outlay | [10 empty] | Project on-going
|  | School Buildings |  |  | Cabayugan | 6889500 | 2024-02-22 | 2024-07-20 | 73.02% | 2190587.76 |  | By contract
Construction of Standard Day Care Center, Brgy. Manalo
| 3.0 Capital Outlay | [10 empty] | Project on-going
|  | School Buildings |  |  | Manalo | 5437195 | 2024-02-22 | 2024-07-20 | 87.24% | 2762467.4 |  | By contract
We hereby certify that we have reviewed the contents and hereby attest to | Construction of Standard Day Care Center, Brgy. Sta. Cruz
the veracity and correctness of the data of information contained in this | 3.0 Capital Outlay | [10 empty] | Project on-going
|  | School Buildings |  |  | Sta. Cruz | 5572294 | 2024-02-22 | 2024-07-20 | 75.63% | 66000 |  | By contract
Completion of Public Market at Brgy. Matahimik
| 3.0 Capital Outlay | [10 empty] | Project on-going
|  | Markets |  |  | Matahimik | 39606355.06 | 2023-11-22 | 2024-06-18 | 91.43% |  |  | By contract
Construction of Salvacion Public Market Phase II ( Water Supply Drilling, Mechanical and Scaling and Deboning Area)
| 3.0 Capital Outlay | [10 empty] | Project for testing/
|  | Markets |  |  | Salvacion | 4200000 | 2023-12-26 | 2024-03-24 | 100% | 91200 |  | commissioning
Completion of Multi-Purpose Building , Brgy. Tagumpay
| 3.0 Capital Outlay | [10 empty] | Project on-going
|  | Markets |  |  | Tagumpay | 3384155 | 2024-02-22 | 2024-05-21 | 98.03% | 489903.1 |  | By contract
Construction of Buenavista Wharf Extension
| 3.0 Capital Outlay | [10 empty] | Project completed
|  | Other Structures |  |  | Buenavista | 10000000 | 2024-02-22 | 2024-07-20 | 100% | 8390096.15 |  | By contract
Construction of Bagong Bayan Wharf Extension
| 3.0 Capital Outlay | [10 empty] | Project on-going
|  | Other Structures |  |  | Bagong Bayan | 10000000 | 2024-02-22 | 2024-07-20 | 75.16% | 7136711.44 |  | By contract
Construction of Covered Gym at Tiniguiban Elementary School, Brgy. Tiniguiban
| 3.0 Capital Outlay | [10 empty] | Project on-going
|  | Other Structures |  |  | Tiniguiban | 9859028 | 2024-02-22 | 2024-08-19 | 39.27% | 2575515.64 |  | By contract
Construction of Covered Gym at Employees Village, Brgy. San Jose
| 3.0 Capital Outlay | [10 empty] | Project on-going
|  | Other Structures |  |  | San Jose | 9859028 | 2024-02-22 | 2024-08-19 | 63% | 2500572.51 |  | By contract
Completion of Bus and Jeepney Terminal ( Covered Walk, Fix Louvers, Guardhouse, Tiles, Food Stalls and Gates)
| 3.0 Capital Outlay | [10 empty] | Project on-going
|  | Other Structures |  |  | Irawan | 21500000 | 2024-04-08 | 2024-12-03 | 3.86% |  |  | By contract
Completion of GSO Compound ( Cement Storage, Driveway, Fence and Gate), Brgy. Sta. Monica
3.0 Capital Outlay
|  | Other Structures |  |  | Sta. Monica | 16200050 | [5 empty] | Unimplemented
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of tha data or information contained in this document.
APPROVED:
|  | ENGR. ALBERTO P. JIMENEZ |  | REGINA S. CANTILLO
|  | City Engineer/Vice Chairman |  | City Budget Officer
LUCILO R. BAYRON
City Mayor