## September 2024 v10.15.2024 SBDP
Annex C
LOCAL GOVERNMENT SUPPORT FUND-SUPPORT TO BARANGAY DEVELOPMENT PROGRAM
Report on Fund Utilization and Status of Program/Project Implementation
For the Quarter Ended September 30, 2024
Fund Source | Date of Notice of Authority to Debit Account Issued (NADAI) | Type of Program/Project | Name of Title of Program/Poject | Specific Location | Mechanism/ Mode of Implementation | Estimated Number of Beneficiaries | Amount |  |  | Estimated Period of Completion (month and year) | Remarks on Program/Project Status
[7 empty] | Received | Obligation | Disbursement
SARO-LGRCB-23-0017442 | 2023-06-06 | Local Government Support Fund - Support to the Barangay Development Program of NTF-ELCAC | Concreting of Farm-to-Market Road at Bgy. Marufinas | Bgy. Marufinas, Puerto Princesa City, Palawan | By Contract |  | 6606882.16 | 6595536.54 | 6595536.54 | November 2023 | % of Physical Completion: 100% Other Remarks: Unutilized balance for refund to BTr - P11,345.62 | 0 | 11345.62
SARO-LGRCB-23-0017442 | 2023-06-06 | Local Government Support Fund - Support to the Barangay Development Program of NTF-ELCAC | Solar Electrification at Bgy. New Panggangan | Bgy. New Panggangan, Puerto Princesa City, Palawan | By Contract |  | 6606882.16 | 6583118.28 | 6477341.5 | February 2024 | % of Physical Completion: 100% Other Remarks: Taxes withheld to be remitted - P105,776.78 Unutilized balance for refund to BTr - P23,763.88 | 105776.78 | 23763.88
SARO-LGRCB-23-0017442 | 2023-06-06 | Local Government Support Fund - Support to the Barangay Development Program of NTF-ELCAC | Rehabilitation of Farm-to-Market Road at Bgy. Tagabinit | Bgy. Tagabinit, Puerto Princesa City, Palawan | By Contract |  | 6606882.16 | 3211382.42 | 2890244.18 | November 2023 | % of Physical Completion: 48.67% Other Remarks: Retention money - P321,138.24 | 321138.24
Certified correct by: | [6 empty] | Attested by:
MARIA REGINA S. CANTILLO |  |  |  | CHARLITO B. PADUL |  |  |  | LUCILO R. BAYRON
City Budget Officer |  |  |  | City Accountant |  |  |  | City Mayor
JEROME M. PADRONES
City Treasurer
JOVENEE C. SAGUN
City Planning and Development Coordinator
Note on K9: MDBL: Actual completion date based on statement of time elapsed and POW
Note on K10: MDBL: Actual completion date based on statement of time elapsed and POW
Note on K11: MDBL: Based on latest statement of time elapsed and POW

## September 2024 v10.15.2024 FA
Annex C
LOCAL GOVERNMENT SUPPORT FUND-FINANCIAL ASSISTANCE TO LOCAL GOVERNMENT UNITS
Report on Fund Utilization and Status of Program/Project Implementation
For the Quarter Ended September 30, 2024
Fund Source | Date of Notice of Authority to Debit Account Issued (NADAI) | Type of Program/Project | Name of Title of Program/Poject | Specific Location | Mechanism/ Mode of Implementation | Estimated Number of Beneficiaries | Amount |  |  | Estimated Period of Completion (month and year) | Remarks on Program/Project Status
[7 empty] | Received | Obligation | Disbursement
SARO-LGRCB-24-0004622 | 2024-07-04 | Local Government Support Fund - Financial Assistance to LGUs, FY 2024 GAA, RA No. 11975 | Assistance to Indigent Individuals or Families: Food Assistance | Barangay San Miguel, Puerto Princesa City | Through Payroll of Beneficiaries | 2,000 individuals | 3000000 | 2911500 | 2911500 | September 2024 | % of Physical Completion: 100% Other Remarks: Unutilized balance for refund to BTr - P88,500.00 | 0 | 88500
Certified correct by: | [6 empty] | Attested by:
MARIA REGINA S. CANTILLO |  |  |  | CHARLITO B. PADUL |  |  |  | LUCILO R. BAYRON
City Budget Officer |  |  |  | City Accountant |  |  |  | City Mayor
JEROME M. PADRONES
City Treasurer
JOVENEE C. SAGUN
City Planning and Development Coordinator
Note on B9: MDBL: ADA No. Value Date
Note on F9: MDBL: Based on Annex D from CMO
Note on K9: MDBL: Date of liquidation report is 09/10/2024

## Sep 2024 v07.08.2024 Various
Annex D
LOCAL GOVERNMENT SUPPORT FUND
Report on Fund Utilization and Status of Program/Project Implementation
As of September 30, 2024
Fund Source | Date of Notice of Authority to Debit Account Issued (NADAI) | Type of Program/Project | Name of Title of Program/Poject | Specific Location | Mechanism/ Mode of Implementation | Estimated Number of Beneficiaries | Amount |  |  | Estimated Period of Completion (month and year) | Program/Project Status
[7 empty] | Received | Obligation | Disbursement
NADAI for LGSF - AC BATCH 7 | 2019-03-04 | LGSF-AC/Green Green Green Program | Development of Balayong Nature Park | Green City Hall Complex, Bgy. Sta. Monica, Puerto Princesa | By Contract |  | 86865534 | 86834451.4 | 86834451.4 | December 2020 | % of Physical Completion: 100% Other Remarks: Refunded unutilized balance to BTr - P31,082.60 | 31082.6 | Internal note: Obligation and disbursements include notice of disallowance for retention money amounting to P1,223,083.60 although such money was not paid to contractor.
NADAI for LGSF - AC BATCH 12 | 2020-08-17 | Local Government Support Fund - Assistance to Cities (LGSF-AC) | Development of Balayong Nature Park "Recreational Park with Green Parking Space" | Bgy. Sta. Monica, Puerto Princesa City, Palawan | By Contract |  | 20857070 | 19995201.25 | 19995201.25 | January 2023 | % of Physical Completion: 100% Other Remarks: Unutilized balance for refund to BTr - P861,868.75 | 861868.75 | Internal note: Obligation and disbursements include notice of disallowance for retention money amounting to P1,223,083.60 although such money was not paid to contractor.
SARO-LGRCB-23-0017442 | 2023-06-06 | Local Government Support Fund - Support to the Barangay Development Program of NTF-ELCAC | Concreting of Farm-to-Market Road at Bgy. Marufinas | Bgy. Marufinas, Puerto Princesa City, Palawan | By Contract |  | 6606882.16 | 6595536.54 | 6595536.54 | November 2023 | % of Physical Completion: 100% Other Remarks: Unutilized balance for refund to BTr - P11,345.62 | 0 | 11345.62
SARO-LGRCB-23-0017442 | 2023-06-06 | Local Government Support Fund - Support to the Barangay Development Program of NTF-ELCAC | Solar Electrification at Bgy. New Panggangan | Bgy. New Panggangan, Puerto Princesa City, Palawan | By Contract |  | 6606882.16 | 6583118.28 | 6477341.5 | February 2024 | % of Physical Completion: 100% Other Remarks: Taxes withheld to be remitted - P105,776.78 Unutilized balance for refund to BTr - P23,763.88 | 105776.78 | 23763.88
SARO-LGRCB-23-0017442 | 2023-06-06 | Local Government Support Fund - Support to the Barangay Development Program of NTF-ELCAC | Rehabilitation of Farm-to-Market Road at Bgy. Tagabinit | Bgy. Tagabinit, Puerto Princesa City, Palawan | By Contract |  | 6606882.16 | 3211382.42 | 2890244.18 | November 2023 | % of Physical Completion: 48.67% Other Remarks: Retention money - P321,138.24 | 321138.24
SARO-LGRCB-24-0004622 | 2024-07-04 | Local Government Support Fund - Financial Assistance to LGUs, FY 2024 GAA, RA No. 11975 | Assistance to Indigent Individuals or Families: Food Assistance | Barangay San Miguel, Puerto Princesa City | Through Payroll of Beneficiaries | 2,000 individuals | 3000000 | 2911500 | 2911500 | September 2024 | % of Physical Completion: 100% Other Remarks: Unutilized balance for refund to BTr - P88,500.00
Certified correct by: | [6 empty] | Attested by:
MARIA REGINA S. CANTILLO |  |  |  | CHARLITO B. PADUL |  |  |  | LUCILO R. BAYRON
City Budget Officer |  |  |  | City Accountant |  |  |  | City Mayor
JEROME M. PADRONES
City Treasurer
JOVENEE C. SAGUN
City Planning and Development Coordinator
Note on B14: MDBL: ADA No. Value Date
Note on F14: MDBL: Based on Annex D from CMO
Note on K10: MDBL: Actual completion date based on Certificate of Completion
Note on K11: MDBL: Actual completion date based on statement of time elapsed and POW
Note on K12: MDBL: Actual completion date based on statement of time elapsed and POW
Note on K13: MDBL: Based on latest statement of time elapsed and POW
Note on K14: MDBL: Date of liquidation report is 09/10/2024