## Form 7 - DFU
FDP Form 7 - 20% COMPONENT OF THE IRA UTILIZATION
UTILIZATION OF THE 20% OF THE NATIONAL TAX ALLOTMENT
| REGION: |  | MIMAROPA |  |  | CALENDAR YEAR: | 2024
| PROVINCE: |  | PALAWAN |  |  | QUARTER: | 4
| CITY/MUNICIPALITY: |  | CITY OF PUERTO PRINCESA
Code | Program / Project |  |  |  | Location | Total Cost | Date Started | Target Completion | Project Status |  | No. of Extension, if any | Remarks
[9 empty] | % of | Total Cost
[9 empty] | Completion | Incurred to Date
ECONOMIC DEVELOPMENT
Completion of Kamuning Public Market Site Development (Road, Parking, Sidewalk, and Drainage)
8918-3(23) | 3.0 Capital Outlay | [10 empty] | Project completed
|  | Other Land Improvements |  |  | Kamuning | 26628000 | 2024-02-22 | 2024-08-19 | 100% | 25538883.32 |  | October 3, 2024
Site Development of Baywalk Public Market (Road, Parking, Sidewalk and Drainage)
8918-4(23) | 3.0 Capital Outlay | [10 empty] | Project suspended
|  | Other Land Improvements |  |  | Matahimik | 34367000 | 2024-02-22 | 2024-11-02 | 74.94% | 16672286.36 |  | due to illegal settlers
Completion of Macarascas Mini City Hall Perimeter Fence
8918-5(23) | 3.0 Capital Outlay | [10 empty] | Project completed
|  | Other Land Improvements |  |  | Macarascas | 3462221 | 2024-02-22 | 2024-05-21 | 100% | 3396382.81 |  | June 19, 2024
Completion of Irawan Agri-Trading Center Fence
8918-6(23) | 3.0 Capital Outlay | [10 empty] | Project completed
|  | Other Land Improvements |  |  | Irawan | 6975000 | 2024-02-22 | 2024-07-20 | 100% | 6776610.65 |  | September 18, 2024
Site Development of Napsan Mini City Hall ( Road, Parking, Sidewalk and Drainage)
| 3.0 Capital Outlay | [10 empty] | Project on hold due
8918-8(23) |  | Other Land Improvements |  |  | Napsan | 12453000 | 2024-02-22 | 2024-07-20 | 49.59% | 6059055.69 |  | to land dispute
Site Development of Macarascas Mini City Hall ( Road, Parking, Sidewalk and Drainage)
| 3.0 Capital Outlay | [10 empty] | Project completed
|  | Other Land Improvements |  |  | Macarascas | 15000000 | 2024-02-22 | 2024-09-03 | 100% | 12293096.69 |  | October 1, 2024
8918-9(23)
Site Development of Salvacion Public Market (Road, Parking, Sidewalk and Drainage)
| 3.0 Capital Outlay | [10 empty] | Project completed
|  | Other Land Improvements |  |  | Salvacion | 20000000 | 2024-02-22 | 2024-09-18 | 100% | 19576274.85 |  | June 6, 2024
8918-10(23)
| Construction of Kamuning Public Market Perimeter Fence and Landscape | [10 empty] | Project terminated for convenience of the LGU
3.0 Capital Outlay
|  | Other Land Improvements |  |  | Kamuning | 6069520 | 2024-02-22 | 2024-07-20 | 4.38%
8918-11(23)
Construction of New City Cemetery Phase V
| 3.0 Capital Outlay | [10 empty] | Project on-going
|  | Other Land Improvements |  |  | Sta. Lourdes | 30000000 | 2024-10-01 | 2025-02-27 | 51.76% | 15113144.22 |  | By contract
8918-13(23)
| Construction of New Muslim Cemetery Perimeter Fence, Brgy. San Jose | [10 empty] | Project physically completed
3.0 Capital Outlay
|  | Other Land Improvements |  |  | San Jose | 2334700 | 2024-04-29 | 2024-08-11 | 100% | 2124726.5 |  | By admin
8918-14(23)
| Concreting of Road Leading to Balsahan River, Brgy. Iwahig | [10 empty] | Project for implementation
3.0 Capital Outlay
|  | Infrastructure Assets - Road Networks |  |  | Iwahig | 13500000 | [5 empty] | By admin
8918-15(23)
Concreting of Access Road to Ubaldo Conde High School, Brgy. Manalo
| 3.0 Capital Outlay | [10 empty] | Project completed
|  | Infrastructure Assets - Road Networks |  |  | Manalo | 3835000 | 2024-09-09 | 2024-12-22 | 100% | 3372449.8 |  | December 14, 2024
8918-16(23)
Replacemet/Concreting of Manalo Extension (Fernandez to Abrea Road) Phase II, Brgy. Milagrosa
| 3.0 Capital Outlay | [10 empty] | Project on-going
|  | Infrastructure Assets - Road Networks |  |  | Milagrosa | 46067000 | 2024-02-22 | 2024-09-18 | 56.48% | 18267743.82 |  | By contract
8918-17(23)
Concreting/Completion of Cactus Road with Drainage System, Brgy. Sta. Monica
| 3.0 Capital Outlay | [10 empty] | Project on-going
|  | Infrastructure Assets - Road Networks |  |  | Sta. Monica | 5539000 | 2024-04-29 | 2024-10-10 | 93.68% | 3889674.59 |  | By contract
8918-18(23)
| Concreting/Completion of Perimeter Road at Magbanua Elementary School, Brgy. San Pedro | [10 empty] | Project for implementation
3.0 Capital Outlay
|  | Infrastructure Assets - Road Networks |  |  | San Pedro | 2992000 |  |  |  | 2288954.78 |  | By admin
8918-19(23)
Concreting of Caramuran Extension at Purok El Rancho, Brgy. Sta. Monica
| 3.0 Capital Outlay | [10 empty] | Project completed
|  | Infrastructure Assets - Road Networks |  |  | Sta. Monica | 7532000 | 2024-02-22 | 2024-05-06 | 100% | 1100693.46 |  | August 23, 2024
8918-22(23)
Concreting of Road Networks at Medina Relocation Site, Brgy. Sicsican
| 3.0 Capital Outlay | [10 empty] | Project completed
|  | Infrastructure Assets - Road Networks |  |  | Sicsican | 10000000 | 2024-02-22 | 2024-07-05 | 100% | 9091689.44 |  | August 24, 2024
8918-23(23)
Concreting of Arcinas Road with Drainage System beside Provincial PNP Station, Brgy. Tiniguiban
| 3.0 Capital Outlay | [10 empty] | Project completed
|  | Infrastructure Assets - Road Networks |  |  | Tiniguiban | 13691000 | 2024-02-22 | 2024-11-17 | 100% | 11970204.64 |  | November 17, 2024
8918-24(23)
Concreting of Road Network at Engineering/Architecture Building and GSO Warehouse
| 3.0 Capital Outlay | [10 empty] | Project on-going
|  | Infrastructure Assets - Road Networks |  |  | Sta. Monica | 24000000 | 2024-02-22 | 2024-09-18 | 61.36% | 3944064.78 |  | By contract
8918-25(23)
Concreting of Laban-Buesa Road (Interior Casuy Road), Brgy. Sta. Monica
| 3.0 Capital Outlay | [10 empty] | Project on-going
|  | Infrastructure Assets - Road Networks |  |  | Sta. Monica | 3150000 | 2024-09-09 | 2025-01-21 | 98.48% | 780918.6 |  | By admin
8918-26(23)
Concreting of Felimon Lagan Road (Interior Hagedorn-Libis Road), Brgy. San Pedro
| 3.0 Capital Outlay | [10 empty] | Project physically
|  | Infrastructure Assets - Road Networks |  |  | San Pedro | 9884000 | 2024-02-22 | 2024-10-03 | 100% | 8838941.88 |  | completed
8918-30(23)
Concreting of VISAPA Road 1 with Drainage Syatem, Brgy. Irawan
| 3.0 Capital Outlay | [10 empty] | Project completed
|  | Infrastructure Assets - Road Networks |  |  | Irawan | 10000000 | 2024-02-29 | 2024-07-27 | 100% | 9875209.29 |  | October 10, 2024
8918-32-a(23)
Road Reblocking of Paduga Road (National Highway to Sampaloc Street, Brgy. Sta. Monica)
| 3.0 Capital Outlay | [10 empty] | Project completed
|  | Infrastructure Assets - Road Networks |  |  | Sta. Monica | 10764000 | 2024-06-26 | 2024-11-07 | 100% | 10404120.77 |  | November 7, 2024
8918-32-b(23)
| Road Reblocking of Salve Regina Road, Brgy. Tiniguiban | [10 empty] | Project physically
| 3.0 Capital Outlay | [10 empty] | completed
|  | Infrastructure Assets - Road Networks |  |  | Tiniguiban | 261500 | 2004-07-01 | 2024-07-15 | 100% | 247114 |  | By admin
8918-32-c(23)
| Road Reblocking of Parangue Road, Brgy. Sicsican | [10 empty] | Project physically
| 3.0 Capital Outlay | [10 empty] | completed
|  | Infrastructure Assets - Road Networks |  |  | Sicsican | 813500 | 2024-07-15 | 2024-07-29 | 100% | 785248 |  | By admin
8918-32-d(23)
Road Reblocking of Manalo Street (H. Mendoza Street to Fernandez Street)
| 3.0 Capital Outlay | [10 empty] | Project on-going
|  | Infrastructure Assets - Road Networks |  |  | Various Brgys. | 9996500 | 2024-06-08 | 2024-10-20 | 95.5% | 6294047.57 |  | By admin
8918-32-e(23)
| Asphalt Overlay of Burgos Street, Various Barangays | [10 empty] | Project physically
| 3.0 Capital Outlay | [10 empty] | completed
|  | Infrastructure Assets - Road Networks |  |  | Various Brgys. | 9265000 | 2024-06-13 | 2024-07-01 | 100% | 9198210.85 |  | By admin
8918-32-f(23)
| Asphalt Overlay of H. Mendoza Street | [10 empty] | Project physically
| 3.0 Capital Outlay | [10 empty] | completed
|  | Infrastructure Assets - Road Networks |  |  | Various Brgys. | 10066500 | 2024-04-22 | 2024-07-11 | 100% | 10028787.26 |  | By admin
8918-33-a(23)
| Asphalt Overlay of Palanca Road | [10 empty] | Project physically
| 3.0 Capital Outlay | [10 empty] | completed
|  | Infrastructure Assets - Road Networks |  |  | Various Brgys. | 1899000 | 2024-08-19 | 2024-08-27 | 100% | 1873751 |  | By admin
8918-33-b(23)
Asphalt Overlay of E. Valencia Street
| 3.0 Capital Outlay | [10 empty] | Project completed
|  | Infrastructure Assets - Road Networks |  |  | Various Brgys. | 9536500 | 2024-03-05 | 2024-04-19 | 100% | 9437808.43 |  | By admin
8918-33-c(23)
Asphalt Overlay of City PNP Entrance
| 3.0 Capital Outlay | [10 empty] | Project completed
|  | Infrastructure Assets - Road Networks |  |  | San Pedro | 1664000 | 2024-07-30 | 2024-08-13 | 100% | 1617401.45 |  | By admin
Concreting of Katarungan Road (Runway to Baltan Catholic Church)
8918-33-d(23) | 3.0 Capital Outlay | [10 empty] | Project on-going
|  | Infrastructure Assets - Road Networks |  |  | Various Brgys. | 3470100 | 2024-11-26 | 2025-04-09 | 34.28% | 2800113.26 |  | By admin
| Concreting of Access Road to Martha Ville Subdivision, Brgy. Irawan | [10 empty] | Project physically completed
8918-33-e(23) | 3.0 Capital Outlay
|  | Infrastructure Assets - Road Networks |  |  | Irawan | 10000000 | 2024-02-22 | 2024-05-05 | 100% | 5555538.31 |  | By contract
| Concreting of San Juan Road (Libis Road to Kalikasan Homes), Brgy. San Pedro | [10 empty] | Project physically completed
8918-33-f(23) | 3.0 Capital Outlay
|  | Infrastructure Assets - Road Networks |  |  | San Pedro | 7406500 | 2024-02-22 | 2024-06-05 | 100% | 6667054.77 |  | By contract
| 10% PRDP Counterpart - FMR Town Site, Macarascas to Purok Cabairan, Brgy. Manalo | [10 empty] | Project for implementation
8918-33-g(23) | 3.0 Capital Outlay
|  | Infrastructure Assets - Road Networks |  |  | Manalo | 20000000 | [5 empty] | By contract
| Concreting of Farm-to-Market Road Leading to Bisor Phase II, Brgy. Bacungan | [10 empty] | Project physically completed
8918-33-h(23) | 3.0 Capital Outlay
|  | Infrastructure Assets - Road Networks |  |  | Bacungan | 5000000 | 2024-02-22 | 2024-07-20 | 100% | 4581307.8 |  | By contract
Concreting/Completion of FMR from Purok Anonang to Purok Star Apple (Verosel), Brgy. Sicsican
8918-7(23) | 3.0 Capital Outlay | [10 empty] | Project completed
|  | Infrastructure Assets - Road Networks |  |  | Sicsican | 27369000 | 2024-02-20 | 2024-10-10 | 100% | 24743849.59 |  | November 2, 2024
Concreting of Farm-to-Market Road Phase II, Brgy. Marufinas
8918-12(23) | 3.0 Capital Outlay | [10 empty] | Project completed
|  | Infrastructure Assets - Road Networks |  |  | Marufinas | 10000000 | 2024-06-25 | 2024-11-21 | 100% | 9876460.96 |  | October 4, 2024
| Concreting of Puting Buhangin Farm-to-Market Road, Brgy. Mangingisda | [10 empty] | Project physically completed
3.0 Capital Outlay
8918-31(23) |  | Infrastructure Assets - Road Networks |  |  | Mangingisda | 10000000 | 2024-02-22 | 2024-07-05 | 100% | 9000549.07 |  | By contract
Construction of Hanging Bridge at Purok 5, Brgy. Inagawan-Sub Colony
3.0 Capital Outlay
8918-20(23) |  | Infrastructure Assets - Road Networks |  |  | Inagawan-Sub | 9250000 | [5 empty] | Unimplemented
Construction of Hanging Bridge at No. 2 at Sitio Tagnaya
| 3.0 Capital Outlay | [10 empty] | Project on-going
8918-21(23) |  | Infrastructure Assets - Road Networks |  |  | Concepcion | 15500000 | 2024-02-22 | 2025-01-16 | 72.97% | 11027252.35 |  | By contract
Completion of Busngol RC Box Culvert ( Concreting of Approach and Slope Protection), Brgy. Sta. Lourdes
| 3.0 Capital Outlay | [10 empty] | Project completed
8918-28(23) |  | Infrastructure Assets - Road Networks |  |  | Sta. Lourdes | 7532500 | 2024-02-22 | 2024-08-19 | 100% | 4507372.82 |  | August 19, 2024
Completion of Sidewalk and Slope Protection at Balayong People's Park
| 3.0 Capital Outlay | [10 empty] | Project completed
8918-29(23) |  | Infrastructure Assets - Road Networks |  |  | Sta. Monica | 7044000 | 2024-02-22 | 2024-05-06 | 100% | 6897293.96 |  | May 30, 2024
| Completion of Sidewalk , Curb and Gutter at Suha Road. Brgy. San Jose | [10 empty] | Project for
| 3.0 Capital Outlay | [10 empty] | implementation
8918-27(23) |  | Infrastructure Assets - Road Networks |  |  | San Jose | 3247500 |  |  |  | 2015721.74 |  | By admin
| Construction of Loading and Unloading Bay along Manalo Street (PNS, PSU-LES, and PP Pilot ES) | [10 empty] | Project physically completed
3.0 Capital Outlay
|  | Infrastructure Assets - Road Networks |  |  | Various Brgys. | 4780000 | 2024-03-02 | 2024-06-29 | 100% | 4394579.39 |  | By contract
8918-1(23) | Construction of Slope Protection at Maoyon Bridge, Brgy. Maoyon
| 3.0 Capital Outlay | [10 empty] | Project completed
|  | Infrastructure Assets - Road Networks |  |  | Maoyon | 5000000 | 2024-03-02 | 2024-06-20 | 100% | 4971413.43 |  | June 20, 2024
8918-2(23) | Rehabilitation of Water Supply System, Brgy. Bagong Bayan | [10 empty] | Project physically
| 3.0 Capital Outlay | [10 empty] | completed
|  | Water Supply System |  |  | Bagong Bayan | 5000000 | 2024-05-15 | 2024-10-11 | 100% | 4854830.21 |  | By admin
Development of Level III Water System in Barangay Maoyon and Manalo
3.0 Capital Outlay
|  | Water Supply System |  |  | Various Brgys. | 4000000 | [5 empty] | Unimplemented
| Rehabilitation/Improvement of Plaza Quartel (Fence, Gate, Landscape, Public Toilet, Admin Office, Information, Monument and Amphitheater with Stage), Brgy. Liwanag | [10 empty] | Project suspended due to excavated human fossil in the area
3.0 Capital Outlay
|  | Parks, Plazas and Monuments |  |  | Liwanag | 15979402 | 2024-04-15 | 2024-09-11 | 21.04%
Construction of Two-Storey PNP Building , Brgy. Luzviminda
| 3.0 Capital Outlay | [10 empty] | Project on-going
|  | Buildings |  |  | Luzviminda | 25194858 | 2024-04-08 | 2025-01-02 | 93.72% | 21638201.81 |  | By contract
Renovation of Old Terminal Building - Offices, Brgy. San Jose
| 3.0 Capital Outlay | [10 empty] | Project on-going
|  | Buildings |  |  | San Jose | 58473159.94 | 2024-05-03 | 2025-02-16 | 54.08% | 28083430.05 |  | By contract
Completion of City Engineering and Architecture Building ( Fixture, Office Furniture)
| 3.0 Capital Outlay | [10 empty] | Project on-going
|  | Buildings |  |  | Sta. Monica | 49618597 | 2024-04-08 | 2025-05-08 | 35.63% |  |  | By contract
| Construction of Standard Day Care Center, Brgy. Kamuning | [10 empty] | Project physically completed
3.0 Capital Outlay
|  | School Buildings |  |  | Kamuning | 5779474 | 2024-02-22 | 2024-07-20 | 100% | 3098404.93 |  | By contract
Construction of Standard Day Care Center, Purok Manturon, Brgy. Cabayuygan
| 3.0 Capital Outlay | [10 empty] | Project completed
|  | School Buildings |  |  | Cabayugan | 6889500 | 2024-02-22 | 2024-07-20 | 100% | 6759011.68 |  | July 30, 2024
| Construction of Standard Day Care Center, Brgy. Manalo | [10 empty] | Project physically completed
3.0 Capital Outlay
|  | School Buildings |  |  | Manalo | 5437195 | 2024-02-22 | 2024-07-20 | 100% | 2780467.4 |  | By contract
Construction of Standard Day Care Center, Brgy. Sta. Cruz
| 3.0 Capital Outlay | [10 empty] | Project completed
|  | School Buildings |  |  | Sta. Cruz | 5572294 | 2024-02-22 | 2024-07-20 | 100% | 5469869.48 |  | August 19, 2024
| Completion of Public Market at Brgy. Matahimik | [10 empty] | Project physically completed
3.0 Capital Outlay
|  | Markets |  |  | Matahimik | 39606355.06 | 2023-11-22 | 2024-06-18 | 100% |  |  | By contract
| Construction of Salvacion Public Market Phase II ( Water Supply Drilling, Mechanical and Scaling and Deboning Area) | [10 empty] | Project physically completed; for testing/commissioning
3.0 Capital Outlay
|  | Markets |  |  | Salvacion | 4200000 | 2023-12-26 | 2024-03-24 | 100% | 91200 |  | By contract
| Completion of Multi-Purpose Building , Brgy. Tagumpay | [10 empty] | Project physically completed
3.0 Capital Outlay
|  | Markets |  |  | Tagumpay | 3384155 | 2024-02-22 | 2024-05-21 | 100% | 3062801.49 |  | By contract
Construction of Buenavista Wharf Extension
| 3.0 Capital Outlay | [10 empty] | Project completed
|  | Other Structures |  |  | Buenavista | 10000000 | 2024-02-22 | 2024-07-20 | 100% | 9854151.13 |  | June 7, 2024
Construction of Bagong Bayan Wharf Extension
| 3.0 Capital Outlay | [10 empty] | Project completed
|  | Other Structures |  |  | Bagong Bayan | 10000000 | 2024-02-22 | 2024-07-20 | 100% | 9824868.38 |  | August 15, 2024
| Construction of Covered Gym at Tiniguiban Elementary School, Brgy. Tiniguiban | [10 empty] | Project physically completed
3.0 Capital Outlay
|  | Other Structures |  |  | Tiniguiban | 9859028 | 2024-02-22 | 2024-08-19 | 100% | 8127136.25 |  | By contract
Construction of Covered Gym at Employees Village, Brgy. San Jose
| 3.0 Capital Outlay | [10 empty] | Project completed
|  | Other Structures |  |  | San Jose | 9859028 | 2024-02-22 | 2024-08-19 | 100% | 9676875.34 |  | September 8, 2024
Completion of Bus and Jeepney Terminal ( Covered Walk, Fix Louvers, Guardhouse, Tiles, Food Stalls and Gates)
| 3.0 Capital Outlay | [10 empty] | Project on-going
|  | Other Structures |  |  | Irawan | 21500000 | 2024-04-08 | 2024-12-03 | 80.24% | 13227290.74 |  | By contract
| Completion of GSO Compound ( Cement Storage, Driveway, Fence and Gate), Brgy. Sta. Monica | [10 empty] | Project on-going
3.0 Capital Outlay
|  | Other Structures |  |  | Sta. Monica | 16200050 | 2024-08-23 | 2025-03-01 | 4.97% | 2420504.13 |  | By contract
| Improvemnet/Concreting of Baywalk Road Networks Brgy. Bagong Pag-asa to Brgy. Mandaragat | [10 empty] | Project on-going
3.0 Capital Outlay
|  | Infrastructure Assets - Road Networks |  |  | Mandaragat | 50022500 | 2024-10-21 | 2025-12-29 | 20.86% | 7312118.34 |  | By contract
| Replacement/Concreting of Sampaloc Road with Drainage System, Brgy. San Jose | [10 empty] | Project on-going
3.0 Capital Outlay
|  | Infrastructure Assets - Road Networks |  |  | San Jose | 37500500 | 2024-10-21 | 2025-08-16 | 14.53% | 5566784.31 |  | By contract
| Rehabilitation of Reyandakan Tribal Village Road, Brgy. Maoyon | [10 empty] | Project for
| 3.0 Capital Outlay | [10 empty] | implementation
|  | Infrastructure Assets - Road Networks |  |  | Maoyon | 3927176.34 |  |  |  | 200 |  | By admin
| Rehabilitation of Road at Macarascas Townsite, Brgy. Macarascas | [10 empty] | Project for
| 3.0 Capital Outlay | [10 empty] | implementation
|  | Infrastructure Assets - Road Networks |  |  | Macarascas | 2405000 |  |  |  | 1943915.4 |  | By admin
| Asphalt Overlay of San Jose Public Market Parking Area, Brgy. San Jose | [10 empty] | With purchase request dated Sept. 12, 2024
3.0 Capital Outlay
|  | Infrastructure Assets - Road Networks |  |  | San Jose | 551000 |  |  |  | 398523.07 |  | By admin
| Asphalt Overlay of Road from Pier to Baywalk Area, Brgy. Bagong Pag-asa | [10 empty] | Project for
| 3.0 Capital Outlay | [10 empty] | implementation
|  | Infrastructure Assets - Road Networks |  |  | Bagong Pag-asa | 1441500 |  |  |  | 1091176.63 |  | By admin
| GRAND TOTAL |  |  |  |  | 909746313.34 |  |  |  | 473177763.72 |  | 52.01%
We hereby certify that we have reviewed the contents and hereby attest to | We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of tha data or information contained in this document.
the veracity and correctness of the data of information contained in this
document.
APPROVED:
|  | ENGR. ARIES S. GRANDE |  | REGINA S. CANTILLO
|  | Assistant City Engineer |  | City Budget Officer
|  | Officer In-charge | [6 empty] | LUCILO R. BAYRON
City Mayor