## 2022 20% IRA U. 2nd Qtr
FDP Form 7 - 20% Component of the IRA Utilization
20% COMPONENT OF THE IRA UTILIZATION
for the 2nd Quarter, CY 2022
City of Puerto Princesa
Program/ Project |  | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[6 empty] | % of Completion | Total Cost Incured to Date
ECONOMIC SERVICES
ECONOMIC SERVICES
8918-1 | REHABILITATION OF KAPAKUAN FARM-TO-MARKET ROAD, LANGOGAN | LANGOGAN | [6 empty] | For survey
Capital Outlay
| Infrastructure Assets- Roads |  | 25993250
8918-2 | OPENING AND GRAVELLING OF FARM-TO-MARKET ROAD FROM MACANDRING TO MANGGAPIN, LANGOGAN | LANGOGAN | [6 empty] | Updating of POW
Capital Outlay
| Infrastructure Assets- Roads |  | 14000000 | 2022-03-23 | 2022-10-03
8918-3 | COMPLETION OF PERIMETER ROAD AT IWAHIG HERITAGE CENTER, IWAHIG | IWAHIG | [6 empty] | On-going By Admin
Capital Outlay
| Infrastructure Assets- Roads |  | 15834000 | 2022-03-23 | 2022-10-03 |  | 15359111.84
8918-4 | CONCRETING OF ROAD LEADING TO PUI FACILITIES WITH SIDEWALK, DRAINAGE SYSTEM & PARKING AREA AT SITIO MAGARWAK, STA. LOURDES | STA. LOURDES | [6 empty] | Work suspended due to modification of road route. Resume order for approval
Capital Outlay
| Infrastructure Assets- Roads |  | 9122000 | 2022-03-02 | 2022-06-19 |  | 1410947.42
8918-5 | COMPLETION OF BAGONG BAYAN WHARF AND ROAD WAY, BAGONG BAYAN | BAGONG BAYAN | [6 empty] | Updating of POW
Capital Outlay
| Infrastructure Assets- Roads |  | 6597500
8918-6 | COMPLETION OF BUENAVISTA WHARF AND ROAD WAY, BUENAVISTA | BUENAVISTA | [6 empty] | Updating of POW
Capital Outlay
| Infrastructure Assets- Roads |  | 15199500
8918-7 | ROAD REPAIR/CONCRETING OF INTERMITTENT SECTION (MACARASCAS TO SITIO SABANG, CABAYUGAN), MACARASCAS AND CABAYUGAN | MACARASCAS & CABAYUGAN | [6 empty] | Updating of POW
Capital Outlay
| Infrastructure Assets- Roads |  | 18945000
8918-8 | CONCRETING AND WIDENING OF KAMUNING ROAD WITH BOX CULVERT,SIDEWALK AND DRAINAGE SYSTEM PHASE III, KAMUNING | KAMUNING | [6 empty] | On-going By Contract
Capital Outlay
| Infrastructure Assets- Roads |  | 48847250 | 2022-02-03 | 2022-12-11 | 13.2% | 7351135.1
8918-9 | COMPLETION OF CATUMBAL ROAD AT PUROK MAGKAKAISA, LUCBUAN | LUCBUAN | [6 empty] | Updating of POW
Capital Outlay
| Infrastructure Assets- Roads |  | 3857000
8918-10 | CONCRETING OF LUZVIMINDA CEMETERY ROAD, LUZVIMINDA | LUZVIMINDA | [6 empty] | On-going By Contract
Capital Outlay
| Infrastructure Assets- Roads |  | 16240000 | 2022-03-23 | 2022-09-12 | 19.52% | 2412762.1
8918-11 | CONCRETING OF ROAD FROM PUROK KAPALARAN LEADING TO LUZVIMINDA ELEMENTARY SCHOOL SITE, LUZVIMINDA | LUZVIMINDA | [6 empty] | On-going By Contract
Capital Outlay
| Infrastructure Assets- Roads |  | 12728100 | 2022-03-23 | 2022-07-20 | 21.35% | 1888080.72
8918-12 | SITE DEVELOPMENT OF IRAWAN AGRICULTURAL TRADING CENTER (ROAD, DRIVEWAY, PARKING, SIDEWALK AND DRAINAGE), IRAWAN | IRAWAN | [6 empty] | On-going By Contract
Capital Outlay
| Other Land Improvements |  | 50000000 | 2022-03-23 | 2022-06-10 | 3.15% | 47019694.62
8918-13 | CONCRETING OF ACCESS ROAD TO PNP BUILDING, NAPSAN | NAPSAN | [6 empty] | On-going By Contract
Capital Outlay
| Infrastructure Assets- Roads |  | 11774000 | 2022-03-23 | 2022-07-20 | 9.15% | 1748227.83
8918-14 | CONCRETING OF MAGBANUA ROAD (LIBIS TO SCHOOL), SAN PEDRO | SAN PEDRO | [6 empty] | Updating of POW
Capital Outlay
| Infrastructure Assets- Roads |  | 5075000
8918-15 | CONCRETING OF ILANG-ILANG ROAD, SAN MIGUEL | SAN MIGUEL | [6 empty] | Updating of POW
Capital Outlay
| Infrastructure Assets- Roads |  | 2416000
8918-16 | OPENING AND GRAVELLING OF ACCESS ROAD FROM INAGAWAN TO NIA FMR, INAGAWAN | INAGAWAN | [6 empty] | Updating of POW
Capital Outlay
| Infrastructure Assets- Roads |  | 6050000
8918-17 | CONSTRUCTION OF FLOOD CONTROL AT SAN MANUEL CATCHMENT AREA, SAN MANUEL | SAN MANUEL | [6 empty] | For procurement
Capital Outlay
| Flood Control Systems |  | 160000000
8918-18 | CONCRETING OF KAAKBAYAN ROAD NETWORK WITH DRAINAGE SYSTEM, TINIGUIBAN | TINIGUIBAN | [6 empty] | Updating of POW
Capital Outlay
| Infrastructure Assets- Roads |  | 41891000
8918-19 | CONSTRUCTION OF DRAINAGE SYSTEM AT PUROK MAPAGMAHAL (CITY EMPLOYEES VILLAGE), SAN JOSE | SAN JOSE | [6 empty] | For procurement
Capital Outlay
| Infrastructure Assets - Drainage and Slope Protection Structures |  | 10269000
8918-20 | REPLACEMENT/CONSTRUCTION OF MAOYON BRIDGE, MAOYON | MAOYON | [6 empty] | On-going By Contract
Capital Outlay
| Infrastructure Assets - Road Networks - Bridges |  | 28050000 | 2022-03-22 | 2022-09-27 | 12.08% | 4219127.16
8918-22 | CONCRETING OF PUROK ILONGGO FARM-TO-MARKET ROAD, BAHILE | BAHILE | [6 empty] | For implementation
Capital Outlay
| Infrastructure Assets- Roads |  | 30328200 | 2022-03-02 | 2022-10-12 | 1.44% | 3788985.16
8918-24 | CONCRETING OF PAGLALUM TO CEMETERY ROAD PHASE II, MANGINGISDA | MANGINGISDA | [6 empty] | On-going By Contract
Capital Outlay
| Infrastructure Assets- Roads |  | 19701785.5 | 2022-03-02 | 2022-08-28 | 42.53% | 9975547.49
8918-25 | CONSTRUCTION OF DRAINAGE ALONG LACAO STREET (FROM MANALO TO MALVAR ST.), MANINGNING | MANINGNING | [6 empty] | Updating of POW
Capital Outlay
| Infrastructure Assets - Drainage and Slope Protection Structures |  | 22152100
8918-26 | CONSTRUCTION OF REMAINING PORTION OF DRAINAGE WITH SIDEWALK ALONG BURGOS TO BONIFACIO STREET (FROM CANTOR TO APITAN PROPERTIES), MASIPAG | MASIPAG | [6 empty] | For procurement
Capital Outlay
| Infrastructure Assets - Drainage and Slope Protection Structures |  | 3227810
8918-27 | REPLACEMENT/CONCRETING OF MANALO EXTENSION (FERNANDEZ TO ABREA ROAD), MILAGROSA | MILAGROSA | [6 empty] | Updating of POW
Capital Outlay
| Infrastructure Assets- Roads |  | 30662482.5
8918-28 | OPENING AND GRAVELLING OF FARM-TO-MARKET ROAD (PUROK DAM-AY, TUBURAN, PUROK 7 TO CEMETERY). INAGAWAN SUB | INAGAWAN SUB | [6 empty] | Updating of POW
Capital Outlay
| Infrastructure Assets- Roads |  | 20000000
8918-29 | CONCRETING OF CALLE POGI AT PUROK CENTRO, BAGONG SIKAT | BAGONG SIKAT | [6 empty] | For preparation of POW,ABC & DUPA
Capital Outlay
| Infrastructure Assets- Roads |  | 3775000
8918-30 | CONCRETING OF ROAD LEADING TO SEASHORE, MARUYUGON | MARUYUGON | [6 empty] | Updating of POW
Capital Outlay
| Infrastructure Assets- Roads |  | 5075000
8918-31 | CONCRETING OF ROAD LEADING TO HUNDRED CAVES, TAGABINET | TAGABINET | [6 empty] | On-going By Contract
Capital Outlay
| Infrastructure Assets- Roads |  | 14210000 | 2022-03-02 | 2022-05-15 | 37.44% | 1375735.39
8918-32 | CONCRETING OF DHALIA AND CACTUS ROAD, STA. MONICA | STA. MONICA | [6 empty] | Updating of POW
Capital Outlay
| Infrastructure Assets- Roads |  | 4323900
8918-33 | CONCRETING OF YELLOW BELL ROAD, STA. MONICA | STA. MONICA | [6 empty] | On-going By Contract
Capital Outlay
| Infrastructure Assets- Roads |  | 13545900 | 2022-03-23 | 2022-08-04 | 21.72% | 1767231.59
8918-34 | CONCRETING OF SANTA ROAD PHASE II, STA. MONICA | STA. MONICA | [6 empty] | Updating of POW
Capital Outlay
| Infrastructure Assets- Roads |  | 6090000
8918-36 | CONSTRUCTION OF SENIOR CITIZEN AND CHILDREN'S PARK WITH MOVABLE PUPPET SHOW STAGE, STA. MONICA | STA. MONICA | [6 empty] | For bidding
Capital Outlay
| Parks, Plazas and Monuments |  | 16000000
8918-37 | CONCRETING OF RAC FMR TO HIGHWAY (CBFM ROAD), SALVACION | SALVACION | [6 empty] | On-going By Contract
Capital Outlay
| Infrastructure Assets- Roads |  | 15834000 | 2022-03-02 | 2022-06-29 | 3.87% | 49500
8918-38 | CONCRETING OF CABALSA ROAD AT PUROK MULAWIN, SICSICAN | SICSICAN | [6 empty] | On-going By Contract
Capital Outlay
| Infrastructure Assets- Roads |  | 12992000 | 2022-03-23 | 2022-07-05 | 20.55% | 10034679.05
8918-39 | CONCRETING OF ROAD NETWORK AT VALDEZTAMON RELOCATION SITE, SICSICAN | SICSICAN | [6 empty] | On-going By Contract
Capital Outlay
| Infrastructure Assets- Roads |  | 16695900 | 2022-03-23 | 2022-10-18 | 93.2% | 15610687.89
8918-40 | OPENING AND CONCRETING OF ACCESS ROAD FROM MITRA ROAD TO RAMPANO, TAGBUROS | TAGBUROS | [6 empty] | On-going By Contract
Capital Outlay
| Infrastructure Assets- Roads |  | 24395000 | 2022-03-02 | 2022-09-27 | 21.03% | 7876518.14
8918-41 | CONCRETING OF ACCESS ROAD TO BAGONG SILANG RELOCATION SITE, TAGBUROS | TAGBUROS | [6 empty] | Updating of POW
Capital Outlay
| Infrastructure Assets- Roads |  | 3451000
8918-42 | CONCRETING OF STO. NIÑO ROAD (PUROK MASAYA TO PUROK MALIGAYA), MACARASCAS | MACARASCAS | [6 empty] | Updating of POW
Capital Outlay
| Infrastructure Assets- Roads |  | 8647800
8918-43 | CONSTRUCTION OF CABAIRAN CONCRETE FOOTBRIDGE, MANALO | MANALO | [6 empty] | On-going By Contract
Capital Outlay
| Infrastructure Assets - Road Networks - Bridges |  | 9637000 | 2022-03-02 | 2022-09-27 | 2.94% | 1430425.53
8918-44 | CONSTRUCTION OF DRAINAGE AT QUEZON EXTENSION, TAGUMPAY | TAGUMPAY | [6 empty] | For procurement
Capital Outlay
| Infrastructure Assets - Drainage and Slope Protection Structures |  | 1382900
8918-45 | REHABILITATION OF COVERED COURT WITH TOILET, NEW PANGGANGAN | NEW PANGGANGAN | [6 empty] | For implementation
Capital Outlay
| Other Structures |  | 3000000 |  |  |  | 2277731.4
8918-46 | CONSTRUCTION OF COVERED GYM AT MABUHAY RELOCATION SITE, SICSICAN | SICSICAN | [6 empty] | On-going By Contract
Capital Outlay
| Other Structures |  | 8200000 | 2022-03-21 | 2022-08-17 | 60.08% | 4980086.39
8918-48 | CONSTRUCTION OF 2 STOREY MULTIPURPOSE BUILDING, BINDUYAN | BINDUYAN | [6 empty] | For bidding
Capital Outlay
| Buildings - Others |  | 7000000
8918-21 | CONCRETING OF FMR LEADING TO BISOR, BACUNGAN | BACUNGAN | [6 empty] | Work suspended due to right-of-way issue
Capital Outlay
| Infrastructure Assets- Roads |  | 25984000 | 2022-03-02 | 2022-09-12 | 1.14% | 3453377.04
8918-23 | CONCRETING OF FMR FROM SITIO SALENG TO SITIO CANDES, BABUYAN | BABUYAN | [6 empty] | Project terminated due to right-of-way issue
Capital Outlay
| Infrastructure Assets- Roads |  | 24197600 | 2022-03-02 | 2022-08-28 |  | 59250
8918-35 | CONCRETING OF FMR FROM PUROK ANONAS TO PUROK STAR APPLE (VEROSEL FMR), SICSICAN | SICSICAN | [6 empty] | On-going By Contract
Capital Outlay
| Infrastructure Assets- Roads |  | 35220500 | 2022-03-02 | 2022-10-12 | 25.85% | 12767231.06
8918-47 | CONSTRUCTION OF COVERED GYM AT PAGKAKAISA RELOCATION SITE, SICSICAN | SICSICAN | [6 empty] | On-going By Contract
Capital Outlay
| Other Structures |  | 8200000 | 2022-03-23 | 2022-08-19 | 60.02% | 4976119.56
| GRAND TOTAL |  | 896818478 |  |  |  | 161832192.48
We hereby certify that we have reviewed the contents and hereby attest to
the veracity and correctness of the data or information contained in this
document.
APPROVED:
| ENGR. ALBERTO P. JIMENEZ | REGINA S. CANTILLO
| City Engineer/Vice Chairman | City Budget Officer
LUCILO R. BAYRON
City Mayor