## Mar 2026 v04.22.2026 SBDP
Annex C
LOCAL GOVERNMENT SUPPORT FUND-SUPPORT TO BARANGAY DEVELOPMENT PROGRAM
Report on Fund Utilization and Status of Program/Project Implementation
For the Quarter Ended March 31, 2026
Fund Source | Date of Notice of Authority to Debit Account Issued (NADAI) | Type of Program/Project | Name of Title of Program/Poject | Specific Location | Mechanism/ Mode of Implementation | Estimated Number of Beneficiaries | Amount |  |  | Estimated Period of Completion (month and year) | Remarks on Program/Project Status
[7 empty] | Received | Obligation | Disbursement
SARO-LGRCB-23-0017442 | 2023-06-06 | Local Government Support Fund - Support to the Barangay Development Program of NTF-ELCAC | Concreting of Farm-to-Market Road at Bgy. Marufinas | Bgy. Marufinas, Puerto Princesa City, Palawan | By Contract |  | 6606882.16 | 6595536.54 | 6595536.54 | November 2023 | % of Physical Completion: 100% Other Remarks: Unutilized balance with check ready for pick-up - P11,345.62 | 0 | 11345.62
SARO-LGRCB-23-0017442 | 2023-06-06 | Local Government Support Fund - Support to the Barangay Development Program of NTF-ELCAC | Solar Electrification at Bgy. New Panggangan | Bgy. New Panggangan, Puerto Princesa City, Palawan | By Contract |  | 6606882.16 | 6583118.28 | 6583118.28 | February 2024 | % of Physical Completion: 100% Other Remarks: Unutilized balance with check ready for pick-up - P23,763.88 | 0 | 23763.88
SARO-LGRCB-23-0017442 | 2023-06-06 | Local Government Support Fund - Support to the Barangay Development Program of NTF-ELCAC | Rehabilitation of Farm-to-Market Road at Bgy. Tagabinit | Bgy. Tagabinit, Puerto Princesa City, Palawan | By Contract |  | 6606882.16 | 6598392.05 | 6598392.05 | October 2024 | % of Physical Completion: 100.00% Other Remarks: Unutilized balance with check ready for pick-up - P 8,490.11 | 0 | 8490.11
SARO-LGRCB-26-0000828 | 2026-03-26 | Local Government Support Fund - Support to the Barangay Development Program of NTF-ELCAC | Concreting of Farm-to-Market Road at Bgy. Cabayugan | Bgy. Cabayugan | No details yet |  | 10000000 | 0 | 0 | No details yet | Not yet started
SARO-LGRCB-26-0000828 | 2026-03-26 | Local Government Support Fund - Support to the Barangay Development Program of NTF-ELCAC | Concreting of Farm-to-Market Road at Bgy. Inagawan | Bgy. Inagawan | No details yet |  | 10000000 | 0 | 0 | No details yet | Not yet started
SARO-LGRCB-26-0000828 | 2026-03-26 | Local Government Support Fund - Support to the Barangay Development Program of NTF-ELCAC | Construction of Level II Potable Water Supply System at Bgy. Langogan | Bgy. Langogan | No details yet |  | 10000000 | 0 | 0 | No details yet | Not yet started
SARO-LGRCB-26-0000828 | 2026-03-26 | Local Government Support Fund - Support to the Barangay Development Program of NTF-ELCAC | Concreting of Farm-to-Market Road at Bgy. Lucbuan | Bgy. Lucbuan | No details yet |  | 10000000 | 0 | 0 | No details yet | Not yet started
SARO-LGRCB-26-0000828 | 2026-03-26 | Local Government Support Fund - Support to the Barangay Development Program of NTF-ELCAC | Concreting of Farm-to-Market Road at Bgy. Tagburos | Bgy. Tagburos | No details yet |  | 10000000 | 0 | 0 | No details yet | Not yet started
Certified correct by: | [6 empty] | Attested by:
MARIA REGINA S. CANTILLO |  |  |  | CHARLITO B. PADUL |  |  |  | LUCILO R. BAYRON
City Budget Officer |  |  |  | City Accountant |  |  |  | City Mayor
JEROME M. PADRONES
City Treasurer
JOVENEE C. SAGUN
City Planning and Development Coordinator
Note on K9: MDBL: Actual completion date based on statement of time elapsed and POW
Note on K10: MDBL: Actual completion date based on statement of time elapsed and POW
Note on K11: MDBL: Actual completion date based on statement of time elapsed and POW

## Mar 2026 v04.22.2026 FA
Annex C
LOCAL GOVERNMENT SUPPORT FUND-FINANCIAL ASSISTANCE TO LOCAL GOVERNMENT UNITS
Report on Fund Utilization and Status of Program/Project Implementation
For the Quarter Ended March 31, 2026
Fund Source | Date of Notice of Authority to Debit Account Issued (NADAI) | Type of Program/Project | Name of Title of Program/Poject | Specific Location | Mechanism/ Mode of Implementation | Estimated Number of Beneficiaries | Amount |  |  | Estimated Period of Completion (month and year) | Remarks on Program/Project Status
[7 empty] | Received | Obligation | Disbursement
SARO-LGRCB-26-0001015 | 2026-03-30 | Local Government Support Fund - Financial Assistance to LGUs, FY 2026 GAA, RA No. 12314 | Assistance to Indigent Individuals or Families - Food Assistance/Rice Distribution Project | Puerto Princesa City, Palawan | No details yet | No details yet | 48000000 | 0 | 0 | No details yet | Not yet started
Certified correct by: | [6 empty] | Attested by:
MARIA REGINA S. CANTILLO |  |  |  | CHARLITO B. PADUL |  |  |  | LUCILO R. BAYRON
City Budget Officer |  |  |  | City Accountant |  |  |  | City Mayor
JEROME M. PADRONES
City Treasurer
JOVENEE C. SAGUN
City Planning and Development Coordinator
Note on B9: MDBL: ADA No. Value Date

## Mar 2026 v04.22.2026 Vrs
Annex D
LOCAL GOVERNMENT SUPPORT FUND
Report on Fund Utilization and Status of Program/Project Implementation
As of March 31, 2026
Fund Source | Date of Notice of Authority to Debit Account Issued (NADAI) | Type of Program/Project | Name of Title of Program/Poject | Specific Location | Mechanism/ Mode of Implementation | Estimated Number of Beneficiaries | Amount |  |  | Estimated Period of Completion (month and year) | Program/Project Status
[7 empty] | Received | Obligation | Disbursement
NADAI for LGSF - AC BATCH 7 | 2019-03-04 | LGSF-AC/Green Green Green Program | Development of Balayong Nature Park | Green City Hall Complex, Bgy. Sta. Monica, Puerto Princesa | By Contract |  | 86865534 | 86834451.4 | 86834451.4 | December 2020 | % of Physical Completion: 100% Other Remarks: Refunded unutilized balance to BTr - P31,082.60 | 31082.6 | Internal note: Obligation and disbursements include notice of disallowance for retention money amounting to P1,223,083.60 although such money was not paid to contractor.
SARO-LGRCB-23-0017442 | 2023-06-06 | Local Government Support Fund - Support to the Barangay Development Program of NTF-ELCAC | Concreting of Farm-to-Market Road at Bgy. Marufinas | Bgy. Marufinas, Puerto Princesa City, Palawan | By Contract |  | 6606882.16 | 6595536.54 | 6595536.54 | November 2023 | % of Physical Completion: 100% Other Remarks: Unutilized balance with check ready for pick-up - P11,345.62
SARO-LGRCB-23-0017442 | 2023-06-06 | Local Government Support Fund - Support to the Barangay Development Program of NTF-ELCAC | Solar Electrification at Bgy. New Panggangan | Bgy. New Panggangan, Puerto Princesa City, Palawan | By Contract |  | 6606882.16 | 6583118.28 | 6583118.28 | February 2024 | % of Physical Completion: 100% Other Remarks: Unutilized balance with check ready for pick-up - P23,763.88
SARO-LGRCB-23-0017442 | 2023-06-06 | Local Government Support Fund - Support to the Barangay Development Program of NTF-ELCAC | Rehabilitation of Farm-to-Market Road at Bgy. Tagabinit | Bgy. Tagabinit, Puerto Princesa City, Palawan | By Contract |  | 6606882.16 | 6598392.05 | 6598392.05 | October 2024
SARO-LGRCB-26-0000828 | 2026-03-26 | Local Government Support Fund - Support to the Barangay Development Program of NTF-ELCAC | Concreting of Farm-to-Market Road at Bgy. Cabayugan | Bgy. Cabayugan | No details yet |  | 10000000 | 0 | 0 | No details yet | Not yet started
SARO-LGRCB-26-0000828 | 2026-03-26 | Local Government Support Fund - Support to the Barangay Development Program of NTF-ELCAC | Concreting of Farm-to-Market Road at Bgy. Inagawan | Bgy. Inagawan | No details yet |  | 10000000 | 0 | 0 | No details yet | Not yet started
SARO-LGRCB-26-0000828 | 2026-03-26 | Local Government Support Fund - Support to the Barangay Development Program of NTF-ELCAC | Construction of Level II Potable Water Supply System at Bgy. Langogan | Bgy. Langogan | No details yet |  | 10000000 | 0 | 0 | No details yet | Not yet started
SARO-LGRCB-26-0000828 | 2026-03-26 | Local Government Support Fund - Support to the Barangay Development Program of NTF-ELCAC | Concreting of Farm-to-Market Road at Bgy. Lucbuan | Bgy. Lucbuan | No details yet |  | 10000000 | 0 | 0 | No details yet | Not yet started
SARO-LGRCB-26-0000828 | 2026-03-26 | Local Government Support Fund - Support to the Barangay Development Program of NTF-ELCAC | Concreting of Farm-to-Market Road at Bgy. Tagburos | Bgy. Tagburos | No details yet |  | 10000000 | 0 | 0 | No details yet | Not yet started
SARO-LGRCB-26-0001015 | 2026-03-30 | Local Government Support Fund - Financial Assistance to LGUs, FY 2026 GAA, RA No. 12314 | Assistance to Indigent Individuals or Families - Food Assistance/Rice Distribution Project | Puerto Princesa City, Palawan | No details yet | No details yet | 48000000 | 0 | 0 | No details yet | Not yet started
Certified correct by: | [6 empty] | Attested by:
MARIA REGINA S. CANTILLO |  |  |  | CHARLITO B. PADUL |  |  |  | LUCILO R. BAYRON
City Budget Officer |  |  |  | City Accountant |  |  |  | City Mayor
JEROME M. PADRONES
City Treasurer
JOVENEE C. SAGUN
City Planning and Development Coordinator
Note on K10: MDBL: Actual completion date based on statement of time elapsed and POW
Note on K11: MDBL: Actual completion date based on statement of time elapsed and POW
Note on K12: MDBL: Actual completion date based on statement of time elapsed and POW
Note on B18: MDBL: ADA No. Value Date