## TF 4th Qtr 2025
FDP Form 6 - Trust Fund Utilization
CONSOLIDATED QUARTERLY REPORT ON GOVERNMENT PROJECTS, PROGRAMS OR ACTIVITIES
For the Quarter Ending 06/30/2026
REGION: |  |  | MIMAROPA |  |  |  | CALENDAR YEAR: |  | 2026
PROVINCE: |  |  | CITY OF PUERTO PRINCESA (CAPITAL) |  |  |  | QUARTER: | 3
CITY/MUNICIPALITY: |  |  | CITY OF PUERTO PRINCESA (Capital)
Program or Project |  |  |  | Location | Total Cost |  | Date Started | Target Completion Date |  | Project Status |  | No. of Extensions, if any
[10 empty] | % of completion | Total Cost incurred to date |  | Remarks
1 |  | (BUB) CONSTRUCTION OF 2 UNITS HEALTH STATIONS WITH COMPLETE EQUIPMENT |  | Bgy. Marufinas & Babuyan, PPC | 6100000 |  | 2016-01-01 | 2016-12-31 |  | 54.73% | 3338323.6 | 0
2 |  | (BUB) MANGROVE & NIPA PLANTATION |  | Puerto Princesa City | 292424.24 |  | 2016-01-01 | 2016-12-31 |  | 100 | 292424.24 | 0
3 |  | (COMPLETED) ADDITIONAL SOCIAL PENSION BENEFICIARIES (1ST AND 2ND QTR) |  | Puerto Princesa City | 9519000 |  | 2016-01-01 | 2016-12-31 |  | 100 | 9519000 | 0
4 |  | SOCIAL PENSION BENEFICIARIES (COMPLETED) |  | Puerto Princesa City | 8616000 |  | 2016-01-01 | 2016-12-31 |  | 100 | 8616000 | 0
5 |  | (BUB) SEAWEEDS FARMING |  | Puerto Princesa City | 500000 |  | 2016-01-01 | 2016-12-31 |  | 100 | 500000 | 0
6 |  | (BUB) LOBSTER/GREEN GROUPER/SEA CUCUMBER CULTURE |  | Puerto Princesa City | 600000 |  | 2016-01-01 | 2016-12-31 |  | 100 | 600000 | 0
7 |  | FINANCIAL ASSISTANCE TO PPSRNP LAYOUT AND PRINTING OF FIELD GUIDE BOOK |  | Puerto Princesa City | 180000 |  | 2017-01-01 | 2017-12-31 |  | 0 | 0 | 0
8 |  | (BUB) INTEGRATED COMMUNITY FOOD PRODUCTION FOR FISHERFOLK FAMILIES |  | Puerto Princesa City | 1400000 |  | 2016-01-01 | 2016-12-31 |  | 100 | 1400000 | 0
9 |  | (BUB) ESTABLISHMENT OF FURNITURE SHOP |  | Puerto Princesa City | 300000 |  | 2016-01-01 | 2016-12-31 |  | 100 | 300000 | 0
10 |  | (BUB) DUCK EGG PRODUCTION |  | Puerto Princesa City | 285000 |  | 2016-01-01 | 2016-12-31 |  | 100 | 285000 | 0
11 |  | AGRI-PINOY TRADING CENTER |  | Bgy. Irawan, PPC | 40000000 |  | 2016-01-01 | 2016-12-31 |  | 100 | 39999999.99 | 0
12 |  | (BUB) POWER TILLER |  | Puerto Princesa City | 300000 |  | 2016-01-01 | 2016-12-31 |  | 100 | 300000 | 0
13 |  | (BUB) SEAWEED POST HARVEST FACILITY |  | Barangay San Rafael, PPC | 1000000 |  | 2016-01-01 | 2016-12-31 |  | 100 | 1000000 | 0
14 |  | (BUB) RICE THRESHER |  | Puerto Princesa City | 300000 |  | 2016-01-01 | 2016-12-31 |  | 100 | 300000 | 0
15 |  | (BUB) HAND TRACTOR PROJECT |  | Puerto Princesa City | 150000 |  | 2016-01-01 | 2016-12-31 |  | 100 | 150000 | 0
16 |  | (BUB) SMALL DIVERSION DAM |  | Puerto Princesa City | 1200000 |  | 2016-01-01 | 2016-12-31 |  | 0 | 0 | 0
17 |  | CONSTRUCTION OF BHS IN BGY. PRINCESA, SAN MIGUEL, MAUNLAD, BANCAO-BANCAO AND MATAHIMIK |  | Bgy. Princesa, San Miguel, Maunlad, Bancao-Banco, & Matahimik, PPC | 7462500 |  | 2016-01-01 | 2016-12-31 |  | 100 | 6716250 | 0
18 |  | PPCITY COMMUNITY ECOLOGICAL MANAGEMENT INSTITUTE FOR GLOBAL ENVIRONMENT STRATEGIES "IGES" IN HAYAMA, KANAGAWA, JAPAN |  | Puerto Princesa City | 690895.2 |  | 2011-01-01 | 2011-12-31 |  | 100 | 690895.2 | 0
19 |  | SUPPLEMENTARY FEEDING PROGRAM (7TH CYCLE) |  | Puerto Princesa City | 8406000 |  | 2017-06-01 | 2017-12-31 |  | 100 | 8406000 | 0
20 |  | REGULATORY IMPACT ASSESSMENT PROJECT |  | Puerto Princesa City | 700065 |  | 2017-01-01 | 2017-12-31 |  | 0 | 0 | 0
21 |  | (BUB) GILLNET FISHING WITH MOTORIZED BANCA |  | Puerto Princesa City | 1500000 |  | 2016-01-01 | 2016-12-31 |  | 100 | 1500000 | 0
22 |  | (BUB) INTEGRATED COMMUNITY FOOD PRODUCTION |  | Puerto Princesa City | 2200000 |  | 2016-01-01 | 2016-12-31 |  | 100 | 2200000 | 0
2016-12-31
23 |  | (BUB) ORGANIC HOG RAISING |  | Puerto Princesa City | 270000 |  | 2016-01-01 | 2016-12-31 |  | 100 | 270000 | 0
24 |  | (BUB) BAMBOO FURNITURE MAKING OF PAYAO ON CALL HOUSE MAINTENANCE |  | Puerto Princesa City | 282684 |  | 2016-01-01 | 2016-12-31 |  | 100 | 282684 | 0
25 |  | YAMAN PINOY ECO BAG PRODUCTION |  | Puerto Princesa City | 500000 |  | 2016-01-01 | 2016-12-31 |  | 100 | 500000 | 0
26 |  | (BUB) MULTI-CAB SPARE PARTS PROJECT |  | Puerto Princesa City | 495000 |  | 2017-01-01 | 2017-12-31 |  | 100 | 495000 | 0
27 |  | FUND TRANSFER INTENDED FOR SURVEY OF SITIO TAGBARUNGIS, BGY. IWAHIG |  | Bgy. Iwahig, PPC | 1900000 |  | 2016-01-01 | 2016-12-31 |  | 100 | 1900000 | 0
28 |  | SM INVESTMENT CAP MANILA |  | Puerto Princesa City | 60000 |  | 2016-01-01 | 2016-12-31 |  | 72.83 | 43698.21 | 0
29 |  | (BUB) LUBA CULTURE IN CAGE |  | Puerto Princesa City | 1000000 |  | 2016-01-01 | 2016-12-31 |  | 100 | 1000000 | 0
30 |  | (BUB) EMPOWERMENT OF BARANGAYS CHILDREN AND PROTECTION |  | Puerto Princesa City | 1000000 |  | 2016-01-01 | 2016-12-31 |  | 100 | 1000000 | 0
31 |  | ANIMAL BITE |  | Puerto Princesa City | 306000 |  | 2016-01-01 | 2016-12-31 |  | 100 | 306000 | 0
32 |  | PAYMENT FOR TB DOTS PATIENT UNDER PFPR |  | Puerto Princesa City | 87000 |  | 2016-01-01 | 2016-12-31 |  | 57.93% | 50400 | 0
33 |  | FINANCIAL ASSISTANCE FOR THE SERVICES OF 293 EXISTING AND 21 NEW BGY NUTRITION SCHOLARS |  | Puerto Princesa City | 187800 |  | 2016-01-01 | 2016-12-31 |  | 100 | 187800 | 0
34 |  | PQMI REHABILITATION PROJECT |  | Bgy. Sta. Lourdes, PPC | 15000000 |  | 2014-01-01 | 2014-12-31 |  | 100 | 15000000 | 0
35 |  | (BUB) SMALL IRRIGATION PROJECT (BGY. STA. CRUZ) |  | Bgy. Sta. Cruz, PPC | 1000000 |  | 2016-01-01 | 2016-12-31 |  | 100 | 1000000 | 0
36 |  | CLUSTERED SATELLITE CLINICS |  | Bgy. Napsan, Salvacion, Mangingisda, San Rafael, & Cabaguyugan, PPC | 5000000 |  | 2015-01-01 | 2015-12-31 |  | 100 | 5000000 | 0
37 |  | (BUB) NATIVE CHICKEN PRODUCTION AND DISPERSAL PROJECT |  | Puerto Princesa City | 4500000 |  | 2014-01-01 | 2014-12-31 |  | 100 | 4500000 | 0
38 |  | REHABILITATION OF PUERTO PRINCESA CITYS GOAT BREEDING FARM |  | Puerto Princesa City | 390000 |  | 2014-01-01 | 2014-12-31 |  | 100 | 390000 | 0
39 |  | CONSTRUCTION OF NATIONAL CHILD DEVELOPMENT CENTER |  | Bgy. Sta. Monica, PPC | 2300000 |  | 2014-01-01 | 2014-12-31 |  | 83.43 | 1918957.37 | 0
40 |  | (BUB) SHELTERED WORKSHOP CENTER WITH TRAINING FOR PERSONS WITH DISABILITY |  | Puerto Princesa City | 2300000 |  | 2014-01-01 | 2014-12-31 |  | 100 | 2300000 | 0
41 |  | (BUB) SELF-EMPLOYMENT ASSISTANCE KAUNLARAN (SEA-K) |  | Puerto Princesa City | 2505282.09 |  | 2015-01-01 | 2015-12-31 |  | 100 | 2505281.7 | 0
42 |  | DEVELOPMENT OF RELOCATION SITE (AFFECTED FAMILIES OF THE AIRPORT EXPANSION PROJECT) |  | Bgy. Mangingisda, PPC | 34886515.26 |  | 2014-01-01 | 2014-12-31 |  | 85.27 | 29749026.98 | 0
43 |  | (BUB) COMMUNAL IRRIGATION PROJECT (SUPPLEMENTARY) |  | Puerto Princesa City | 3500000 |  | 2015-01-01 | 2015-12-31 |  | 100 | 3500000 | 0
44 |  | (BUB) BAMBOO DEVELOPMENT AND PROCESSING PROJECT |  | Puerto Princesa City | 2500000 |  | 2014-12-01 | 2014-12-31 |  | 100 | 2500000 | 0
45 |  | (BUB) ORGANIC VEGETABLE PRODUCTION THRU GREENHOUSE TECHNOLOGY |  | Puerto Princesa City | 3301995.73 |  | 2014-01-01 | 2014-12-31 |  | 100 | 3301995.73 | 0
46 |  | FOOD PROCESSING (AGRI-FARM PRODUCTS) KITCHEN INCUBATOR |  | Bgy. Simpocan, PPC | 1701900 |  | 2014-01-01 | 2014-12-31 |  | 100 | 1701900 | 0
47 |  | (BUB) SWINE PRODUCTION (BREEDING AND FATTENING) |  | Puerto Princesa City | 690000 |  | 2014-01-01 | 2014-12-31 |  | 100 | 690000 | 0
48 |  | CENTER FOR HEALTH AND DEVELOPMENT IV-B INTENDED FOR IMPLEMENTATION OF DETEC TB |  | Puerto Princesa City | 4763925 |  | 2013-01-01 | 2013-12-31 |  | 100 | 4763925 | 0
49 |  | LGU WINNER OF GAWAD PAMANA NG LAHI |  | Bgy. Bahile & Lucbuan, PPC | 7000000 |  | 2018-01-22 | 2018-12-31 |  | 100 | 7000000 | 0
50 |  | MDG FAMILY- BASED ACTIONS FOR CHILDREN AND THEIR ENVIRONMENT IN THE SLUMS (SDG-FACES) PROJECT |  | Puerto Princesa City | 260000 |  | 2014-01-01 | 2014-12-31 |  | 100 | 260000 | 0
51 |  | (BUB) CAPABILITY BUILDING (BCPC) |  | Puerto Princesa City | 300000 |  | 2015-01-01 | 2015-12-31 |  | 100 | 300000 | 0
52 |  | PERFORMANCE CHALLENGE FUND (PCF) 2017 |  | Puerto Princesa City | 2400000 |  | 2017-01-01 | 2017-12-31 |  | 100 | 2400000 | 0
53 |  | (BUB) PAG-ASA YOUTH ASSOCIATION YOUTH DAY CELEBRATION |  | Puerto Princesa City | 140000 |  | 2015-01-01 | 2015-12-31 |  | 100 | 140000 | 0
54 |  | (BUB) OUT OF SCHOOL YOUTH RESIDENTIAL PROGRAM (MODULE 4 AND 5) |  | Puerto Princesa City | 181818.18 |  | 2015-01-01 | 2015-12-31 |  | 100 | 181818.18 | 0
55 |  | (BUB) WALANG TAMBAY SA BARANGAY |  | Puerto Princesa City | 282684 |  | 2015-01-01 | 2015-12-31 |  | 100 | 282684 | 0
56 |  | (BUB) OUT OF SCHOOL YOUTH RESIDENTIAL PROGRAM MODULE 1, 2 & 3 |  | Puerto Princesa City | 181818.18 |  | 2015-01-01 | 2015-12-31 |  | 100 | 181818.18 | 0
57 |  | (BUB) CONTINUOUS CAPACITY BUILDING FOR PARENT EFFECTIVENESS SESSION (PES) AND DAY CARE WORKERS |  | Puerto Princesa City | 701000 |  | 2015-01-01 | 2015-12-31 |  | 100 | 701000 | 0
58 |  | (BUB) HANDICRAFTS TRAINING AND MANUFACTURING |  | Puerto Princesa City | 530000 |  | 2014-01-01 | 2014-12-31 |  | 100 | 530000 | 0
59 |  | (BUB) GROUP HAND WASHING FACILITY FOR DAY CARE CENTERS |  | Puerto Princesa City | 4402000 |  | 2015-01-01 | 2015-12-31 |  | 100 | 4401999.6 | 0
60 |  | (BUB) SMALL IRRIGATION PROJECT (BGY. TAGABINET) |  | Bgy. Tagabinet, PPC | 2000000 |  | 2016-01-01 | 2016-12-31 |  | 100 | 2000000 | 0
61 |  | TULONG PANGHANAP-BUHAY SA ATING MGA DISADVANTAGED/DISPLACED WORKERS (TUPAD) PROGRAM |  | Puerto Princesa City | 2848000 |  | 2020-10-01 | 2020-12-31 |  | 100 | 2848000 | 0
62 |  | (BUB) PALAWAN ECOLOGICAL ADVENTURE TRAIL PROJECT |  | Puerto Princesa City | 787727.27 |  | 2015-01-01 | 2015-12-31 |  | 100 | 787727.27 | 0
63 |  | CITY LEADERSHIP AND GOVERNANCE PROGRAM (CLGP) |  | Puerto Princesa City | 300000 |  | 2015-01-01 | 2015-12-31 |  | 100 | 300000 | 0
64 |  | SPECIAL LOCAL ROADS FUND (SLRF) |  | Puerto Princesa City | 6845219.94 |  | 2015-01-01 | 2015-12-31 |  | 100 | 6845219.94 | 0
65 |  | (BUB) FINANCIAL ASSISTANCE TO EDUCATIONAL NEEDS OF INDIGENOUS PEOPLE (IP) YOUTH |  | Puerto Princesa City | 701000.99 |  | 2015-09-02 | 2015-12-31 |  | 100 | 701000.99 | 0
66 |  | (BUB) COMMUNAL IRRIGATION PROJECT |  | Puerto Princesa City | 300000 |  | 2015-01-01 | 2015-12-31 |  | 100 | 300000 | 0
67 |  | (BUB) EDUCATIONAL ASSISTANCE FOR OUT OF SCHOOL YOUTHS (OSYS) AND PERSONS WITH DISABILITY (PWD) |  | Puerto Princesa City | 2000000 |  | 2015-01-01 | 2015-12-31 |  | 100 | 2000000 | 0
68 |  | MOTORIZED FISHING BANCA WITH FISHING PARAPHERNALIA PROJECT |  | Puerto Princesa City | 1500000 |  | 2016-12-01 | 2016-12-31 |  | 100 | 1500000 | 0
69 |  | MOTIVATIONAL INCENTIVES/ AWARDS (MR - POLIO SIA 2020) |  | Puerto Princesa City | 170000 |  | 2020-12-10 | 2020-12-31 |  | 100 | 170000 | 0
70 |  | DEVELOPMENT OF MINI PARKS (CASCADING PARK, FRIENDSHIP PARK, PSU GATEWAY PARK AND ROTONDA PARK) |  | Bgy. Sta. Monica, PPC | 16762351 |  | 2021-01-15 | 2021-12-31 |  | 100 | 16762351 | 0
71 |  | COVID-19 VACCINATION AND DEPLOYMENT |  | Puerto Princesa City | 4500000 |  | 2021-09-01 | 2021-12-31 |  | 100 | 4500000 | 0
72 |  | SOCIAL PENSION FOR INDIGENT SENIOR CITIZENS |  | Puerto Princesa City | 13515000 |  | 2020-01-01 | 2020-12-31 |  | 100 | 13515000 | 0
73 |  | SOCIAL AMELIORATION PROGRAM (SAP) FOR PANTAWID PAMILYANG PILIPINO PROGRAM (4PS) BENEFICIARIES |  | Puerto Princesa City | 1354150 |  | 2020-05-11 | 2020-12-31 |  | 100 | 1354150 | 0
74 |  | SPONSORSHIP FOR THE RENOVATION OF VISITORS WAITING SHED |  | Puerto Princesa Underground River | 90000 |  | 2017-01-01 | 2017-12-31 |  | 0 | 0 | 0
75 |  | ESTABLISHMENT OF MATERIALS RECOVERY FACILITY (MRF) |  | Puerto Princesa City | 142500 |  | 2018-03-02 | 2019-03-02 |  | 100 | 142500 | 0
76 |  | FINANCIAL ASSISTANCE FOR VICTIMS AFFECTED BY TYPHOON ODETTE (DONATION) - NATIONAL HOUSING AUTHORITY |  | Puerto Princesa City | 6250000 |  | 2021-12-01 | 2021-12-31 |  | 100 | 6250000 | 0
77 |  | GRANT/SUBSIDY FOR THE BILLETING DEPED SCHOOLS IN FAVOR OF PPCITY |  | Puerto Princesa City | 465000 |  | 2019-09-01 | 2019-12-31 |  | 100 | 465000 | 0
78 |  | PRDP BUAL-BUALAN FARM TO MARKET ROAD |  | Sitio Bual-Bulan, PPC | 31994449.71 |  | 2018-01-01 | 2018-12-31 |  | 100 | 31994449.71 | 0
79 |  | PHILHEALTH CAPITATION FUND |  | Puerto Princesa City | 1427400.61 |  | 2016-01-01 | 2016-12-31 |  | 98.743 | 1409457.6 | 0
80 |  | LIVESTOCK DISPERSAL OF WORKING ANIMALS CARABAO PROJECT |  | Puerto Princesa City | 1526790 |  | 2014-07-01 | 2014-12-31 |  | 100 | 1526790 | 0
81 |  | DEVELOPMENT OF BALAYONG NATURE PARK |  | Bgy. Sta. Monica, PPC | 86865534 |  | 2019-07-01 | 2019-12-31 |  | 100 | 86865534 | 0
82 |  | RECREATIONAL PARK WITH GREEN PARKING SPACE |  | Bgy. Sta. Monica, PPC | 20857070 |  | 2021-01-01 | 2021-12-31 |  | 100 | 20857070 | 0
83 |  | SOCIAL AMELIORATION PROGRAM (SAP) |  | Puerto Princesa City | 184780000 |  | 2020-01-01 | 2020-12-31 |  | 100 | 184780000 | 0
84 |  | FINANCIAL ASSISTANCE FOR VICTIMS AFFECTED BY TYPHOON ODETTE (DONATION) - PHILIPPINE CHARITY SWEEPSTAKES OFFICE (PCSO) |  | Puerto Princesa City | 2000000 |  | 2022-01-01 | 2022-12-31 |  | 100 | 2000000 | 0
85 |  | ONE COVID-19 ALLOWANCE (OCA) |  | Puerto Princesa City | 49316968.75 |  | 2022-01-01 | 2022-12-31 |  | 100 | 49316968.75 | 0
86 |  | UHC - HEALTH PROMOTION PLAYBOOK NO. 3 FOR IMMUNIZATION PROGRAM "BAKUNA CHAMPIONS" |  | Puerto Princesa City | 611821.86 |  | 2022-08-01 | 2022-12-31 |  | 100 | 611821.86 | 0
87 |  | INFORMATION SYSTEM ON TRANSPORT OPERATION IN PUERTO PRINCESA (ISTOPP) |  | Puerto Princesa City | 7500000 |  | 2022-11-01 | 2022-12-31 |  | 100 | 7500000 | 0
88 |  | ENHANCED KADIWA NI ANI AT KITA PROGRAM |  | Puerto Princesa City | 2300000 |  | 2022-05-17 | 2022-12-31 |  | 100 | 2300000 | 0
89 |  | INSTALLATION OF SOLAR STREET LIGHTS IN BGY. BACUNGAN AND BGY. STA. LOURDES |  | Bgy. Bacungan & Sta. Lourdes, PPC | 20000000 |  | 2022-05-27 | 2022-12-31 |  | 100 | 20000000 | 0
90 |  | REGULAR AND TOP-UP FIXED TRANCHE FOR UHC IS 2022 |  | Puerto Princesa City | 1691360 |  | 2022-06-14 | 2022-12-31 |  | 100 | 1691360 | 0
91 |  | FINANCIAL ASSISTANCE FOR VICTIMS AFFECTED BY TYPHOON ODETTE (DONATION) - BANGKO SENTRAL-LUCENA CITY |  | Puerto Princesa City | 20500 |  | 2021-12-01 | 2021-12-31 |  | 100 | 20500 | 0
92 |  | FINANCIAL ASSISTANCE FOR VICTIMS AFFECTED BY TYPHOON ODETTE (DONATION) - CDRRM ZAMBOANGA CITY |  | Puerto Princesa City | 650000 |  | 2022-01-01 | 2022-12-31 |  | 100 | 650000 | 0
93 |  | FINANCIAL ASSISTANCE FOR VICTIMS AFFECTED BY TYPHOON ODETTE (DONATION) - LAND BANK OF THE PHILIPPINES PUERTO PRINCESA BRANCH |  | Puerto Princesa City | 150000 |  | 2021-12-01 | 2021-12-31 |  | 100 | 150000 | 0
94 |  | FINANCIAL ASSISTANCE FOR VICTIMS AFFECTED BY TYPHOON ODETTE (DONATION) - DEVELOPMENT BANK OF THE PHILIPPINES (DBP) - PUERTO PRINCESA CITY |  | Puerto Princesa City | 150000 |  | 2022-01-01 | 2022-12-31 |  | 100 | 150000 | 0
95 |  | FINANCIAL ASSISTANCE FOR VICTIMS AFFECTED BY TYPHOON ODETTE (DONATION) - MUNICIPALITY OF INFANTA, QUEZON |  | Puerto Princesa City | 100000 |  | 2022-01-01 | 2022-12-31 |  | 100 | 100000 | 0
96 |  | FINANCIAL ASSISTANCE FOR VICTIMS AFFECTED BY TYPHOON ODETTE (DONATION) - VIVANT FOUNDATION INC. |  | Puerto Princesa City | 350000 |  | 2021-12-01 | 2021-12-31 |  | 100 | 350000 | 0
97 |  | FINANCIAL ASSISTANCE FOR VICTIMS AFFECTED BY TYPHOON ODETTE (DONATION) - HON. SARA DUTERTE- CARPIO |  | Puerto Princesa City | 500000 |  | 2021-12-01 | 2021-12-31 |  | 100 | 500000 | 0
98 |  | FINANCIAL ASSISTANCE FOR VICTIMS AFFECTED BY TYPHOON ODETTE (DONATION) - PROVINCIAL GOVERNMENT OF DAVAO OCCIDENTAL |  | Puerto Princesa City | 1000000 |  | 2021-12-01 | 2021-12-31 |  | 100 | 1000000 | 0
99 |  | ESTABLISHMENT OF BSMPMODAI MULTICAB SPARE PARTS STORE |  | Puerto Princesa City | 1000000 |  | 2018-10-01 | 2018-12-31 |  | 100 | 1000000 | 0
100 |  | FINANCIAL ASSISTANCE FOR VICTIMS AFFECTED BY TYPHOON ODETTE (DONATION) - DRRMC/ LGU-BAGGAO, CAGAYAN VALLEY |  | Puerto Princesa City | 100000 |  | 2022-02-01 | 2022-12-31 |  | 100 | 100000 | 0
101 |  | T/F FOR TRAVELLING ALLOWANCE OF 318 EXISTING BNS FOR CY 2018 |  | Puerto Princesa City | 365400 |  | 2019-01-01 | 2019-12-31 |  | 100 | 365400 | 0
102 |  | COVID-19 SPECIAL RISK ALLOWANCE |  | Puerto Princesa City | 5487954.55 |  | 2021-01-01 | 2021-12-31 |  | 100 | 5487954.55 | 0
103 |  | CONSTRUCTION OF BAHAY PAG-ASA, BGY. MANGINGISDA, PUERTO PRINCESA CITY |  | Bgy. Mangingisda, PPC | 4944964.25 |  | 2018-12-11 | 2018-12-31 |  | 100 | 4944964.25 | 0
104 |  | DRAINAGE IMPROVEMENT OF SARHENTO ST., KALYE SEKSI, KAAKBAYAN, BGY. TINIGUIBAN |  | Bgy. Tiniguiban, PPC | 6709681 |  | 2018-11-22 | 2018-12-31 |  | 100 | 6709681 | 0
105 |  | SOCIAL PENSION OF INDIGENT SENIOR CITIZENS (COMPLETED) |  | Puerto Princesa City | 74544000 |  | 2018-07-02 | 2018-12-31 |  | 100 | 74544000 | 0
106 |  | CONSTRUCTION/REHABILITATION OF SABANG ROAD, SITIO SABANG, BGY. CABAYUGAN |  | Bgy. Cabayugan, PPC | 1000000 |  | 2013-01-01 | 2013-12-31 |  | 99.98 | 999830 | 0
107 |  | CULTURE OF MARINE FISH IN FLOATING NET CAGES WITH FLOATING COTTAGES |  | Bgy. Tiniguiban, PPC | 2000000 |  | 2014-01-01 | 2014-12-31 |  | 100 | 2000000 | 0
108 |  | PUERTO PRINCESA CITY MANGO PROCESSING FACILITY AND MARKETING CENTER I-REAP (CIVIL WORKS) |  | Puerto Princesa City | 5446260.1 |  | 2017-01-01 | 2017-12-31 |  | 100 | 5446260.1 | 0
109 |  | BUREAU OF FIRE PROTECTION |  | Puerto Princesa City | 2868403.06 |  | 2017-01-01 | 2025-12-31 |  | 98.87 | 2854575.57 | 0
110 |  | MAOYON FLOATING RESTAURANT AND RIVER PICNIC RAFTING |  | Bgy. Maoyon, PPC | 356758 |  | 2018-10-01 | 2018-12-31 |  | 100 | 356758 | 0
111 |  | (COMPLETED) SOCIAL PENSION BENEFICIARIES FOR 1ST AND 2ND QUARTER 2016 |  | Puerto Princesa City | 5319000 |  | 2016-01-01 | 2016-12-31 |  | 100 | 5319000 | 0
112 |  | PUERTO PRINCESA CITY MANGO PROCESSING FACILITY AND MARKETING CENTER I-REAP (ENTERPRISE) |  | Puerto Princesa City | 6711370.71 |  | 2017-01-01 | 2017-12-31 |  | 100 | 6711370.71 | 0
113 |  | SUPPLEMENTARY FEEDING PROGRAM FOR SCHOOL CHILDREN FROM JOLLIBEE FOUNDATION |  | Puerto Princesa City | 11886 |  | 2013-01-01 | 2013-12-31 |  | 0 | 0 | 0
114 |  | CORN PROGRAM- 4 WHEEL DRIVE TRACTOR |  | Puerto Princesa City | 750000 |  | 2016-01-01 | 2016-12-31 |  | 100 | 750000 | 0
115 |  | COMBINE HARVESTER |  | Puerto Princesa City | 480000 |  | 2016-01-01 | 2016-12-31 |  | 100 | 480000 | 0
116 |  | MATCHING GRANT PROGRAM (MNCHN) |  | Puerto Princesa City | 464418.43 |  | 2017-01-01 | 2017-12-31 |  | 100 | 464418.43 | 0
117 |  | (COMPLETED) SOCIAL PENSION BENEFICIARIES |  | Puerto Princesa City | 774000 |  | 2015-01-01 | 2015-12-31 |  | 100 | 774000 | 0
118 |  | WATER REFILLING STATION |  | Puerto Princesa City | 750000 |  | 2018-10-01 | 2018-12-31 |  | 100 | 750000 | 0
119 |  | SOCIAL PENSION PROGRAM |  | Puerto Princesa City | 70812000 |  | 2023-01-01 | 2023-12-31 |  | 100 | 70812000 | 0
120 |  | SOUVENIR ITEMS MAKING AND SELLING |  | Puerto Princesa City | 273888 |  | 2018-10-01 | 2018-12-31 |  | 100 | 273888 | 0
121 |  | PHOTO PRINT, T-SHIRT PRINTING AND MUG PRINTING |  | Puerto Princesa City | 499500 |  | 2018-10-01 | 2018-12-31 |  | 100 | 499500 | 0
122 |  | PHOTO BOOTH AND BIKE RENTAL |  | Puerto Princesa City | 249000 |  | 2018-10-01 | 2018-12-31 |  | 100 | 249000 | 0
123 |  | FLOATING RESTAURANT WITH SOUVENIR T-SHIRT PRODUCTION |  | Puerto Princesa City | 194340 |  | 2018-10-01 | 2018-12-31 |  | 100 | 194340 | 0
124 |  | BEACH ACCESSORIES RENTALS |  | Puerto Princesa City | 515660 |  | 2018-10-01 | 2018-12-31 |  | 100 | 515660 | 0
125 |  | PERFORMANCE CHALLENGE FUND (PCF) |  | Puerto Princesa City | 3400000 |  | 2017-01-01 | 2017-12-31 |  | 100 | 3400000 | 0
126 |  | HANDICRAFT MAKING AND T-SHIRT PRINTING |  | Puerto Princesa City | 259687.5 |  | 2018-10-01 | 2018-12-31 |  | 100 | 259687.5 | 0
127 |  | FIBERGLASS FABRICATION AND BOAT BUILDING |  | Puerto Princesa City | 1000000 |  | 2018-10-01 | 2018-12-31 |  | 100 | 1000000 | 0
128 |  | COMMUNITY BAKERY |  | Puerto Princesa City | 265465 |  | 2018-10-01 | 2018-12-31 |  | 100 | 265465 | 0
129 |  | BOAT SERVICES AND SNORKELING RENTALS |  | Puerto Princesa City | 500000 |  | 2018-10-01 | 2018-12-31 |  | 100 | 500000 | 0
130 |  | FIXED TRANCHE FOR ANNUAL OPERATIONAL PLAN CY 2021 (COVID-19 RESPONSE AND UHC IS) |  | Puerto Princesa City | 1663429 |  | 2021-09-01 | 2021-12-31 |  | 100 | 1663429 | 0
131 |  | INSTALLATION OF SOLAR STREET LIGHTS IN RURAL AREAS |  | Puerto Princesa City | 10000000 |  | 2021-08-01 | 2021-12-31 |  | 100 | 10000000 | 0
132 |  | SPECIAL RISK ALLOWANCE (SRA) AND ACTIVE HAZARD DUTY PAY (AHDP) |  | Puerto Princesa City | 7300000 |  | 2021-01-01 | 2021-12-31 |  | 100 | 7300000 | 0
133 |  | SOLAR STREET LIGHTING PROJECT FOR BGY LANGOGAN, BGY BINDUYAN AND BGY KAMUNING, PUERTO PRINCESA CITY |  | Bgy. Langogan, Binduyan, & Kamuning, PPC | 10000000 |  | 2020-06-25 | 2020-12-31 |  | 100 | 10000000 | 0
134 |  | SURVIVAL T-SHIRT PRINTING AND SELLING |  | Puerto Princesa City | 231140 |  | 2018-10-01 | 2018-12-31 |  | 100 | 231140 | 0
135 |  | BARANGAY NUTRITION SCHOLAR (BNS) |  | Puerto Princesa City | 390400 |  | 2022-07-12 | 2022-12-31 |  | 99.0779 | 386800 | 0
136 |  | FINANCIAL ASSISTANCE TO LGUS AFFECTED BY |  | Puerto Princesa City | 16423361 |  | 2021-12-24 | 2021-12-31 |  | 100 | 16423361 | 0
TYPHOON ODETTE (SARO-LGRCB-21-0013737)
137 |  | FINANCIAL ASSISTANCE TO LGUS AFFECTED BY |  | Puerto Princesa City | 15094853 |  | 2021-12-28 | 2021-12-31 |  | 100 | 15094853 | 0
TYPHOON ODETTE (SARO-LGRCB-21-0013791)
138 |  | FINANCIAL ASSISTANCE TO LGUS AFFECTED BY |  | Puerto Princesa City | 81736000 |  | 2021-12-29 | 2021-12-31 |  | 100 | 81736000 | 0
TYPHOON ODETTE (SARO-LGRCB-21-0013991)
139 |  | SEAWEEDS PRODUCTION AND MARKETING |  | Puerto Princesa City | 12789862.17 |  | 2019-01-01 | 2021-12-31 |  | 100 | 12789862.17 | 0
(PRDP I-REAP)
140 |  | PUERTO PRINCESA CITY MANGO |  | Puerto Princesa City | 5441484.21 |  | 2018-01-01 | 2018-12-31 |  | 100 | 5441484.21 | 0
PROCESSING FACILITY AND MARKETING
CENTER - CIVIL WORKS (PRDP I-REAP)
141 |  | PUERTO PRINCESA CITY MANGO |  | Puerto Princesa City | 6711370.71 |  | 2018-01-01 | 2018-12-31 |  | 100 | 6711370.71 | 0
PROCESSING FACILITY AND MARKETING
CENTER - ENTERPRISE (PRDP I-REAP)
142 |  | CONSTRUCTION AND CONCRETING OF |  | Bgy. Maruyugon & Buenavista, PPC | 119829587.71 |  | 2020-01-01 | 2020-12-31 |  | 100 | 119829587.71 | 0
MARUYUGON TO BUENAVISTA FARM TO
MARKET ROAD (PRDP I-BUILD)
143 |  | DMCI POWER CORPORATION RWMHEEF (ER 1- |  | Puerto Princesa City | 1762814.46 |  | 2020-12-14 | 2026-12-31 |  | 84.1822 | 1483975.19 | 0
94) - DMCI POWER IRAWAN
144 |  | DMCI POWER CORPORATION DLF (ER 1-94) - |  | Puerto Princesa City | 596687.89 |  | 2020-12-14 | 2026-12-31 |  | 50.4846 | 301235.49 | 0
DMCI POWER IRAWAN
145 |  | DELTA P INCORPORATED DLF (ER 1-94) |  | Puerto Princesa City | 995103.08 |  | 2020-06-03 | 2026-12-31 |  | 27.1429 | 270100.14 | 0
146 |  | DELTA P INCORPORATED RWMHEEF (ER 1-94) |  | Puerto Princesa City | 1548767.65 |  | 2020-06-03 | 2026-12-31 |  | 53.6618 | 831096.86 | 0
147 |  | HC-CGPP PALAWAN POWER GEN INC. |  | Puerto Princesa City | 452705.3 |  | 2020-12-14 | 2026-12-31 |  | 0 | 0 | 0
RWMHEEF (ER 1-94)
148 |  | HC-CGPP PALAWAN POWER GEN INC. DLF |  | Puerto Princesa City | 452705.3 |  | 2020-12-14 | 2026-12-31 |  | 0 | 0 | 0
(ER-94)
149 |  | USAID - TUBERCULOSIS IMPLEMENTATION |  | Puerto Princesa City | 32405314.45 |  | 2022-06-13 | 2026-12-31 |  | 83.4335 | 27036882.76 | 0
FRAMEWORK AGREEMENT - TIFA
150 |  | SPECIAL RISK ALLOWANCE (SRA) - CY 2022 GAA |  | Puerto Princesa City | 3494318.18 |  | 2022-09-14 | 2022-12-31 |  | 100 | 3494318.18 | 0
151 |  | CHIKITING BAKUNA DAYS (CBD) CULMINATION |  | Puerto Princesa City | 500000 |  | 2023-03-29 | 2023-12-31 |  | 100 | 500000 | 0
ACTIVITY AND MID-YEAR PLANNING WORKSHOP
152 |  | LIVESTOCK REHABILITATION PROJECT |  | Puerto Princesa City | 26375000 |  | 2023-01-12 | 2023-12-31 |  | 100 | 26375000 | 0
153 |  | COMPLETION OF MANGINGISDA SATELLITE CLINIC |  | Bgy. Mangingisda, San Miguel, Bagong Bayan, PPC | 13650000 |  | 2023-02-01 | 2023-12-31 |  | 100 | 13650000 | 0
PHASE 3, SAN MIGUEL SATELLITE CLINIC PHASE 3,
BAGONG BAYAN SATELLITE CLINIC PHASE 3, AND
NEW CONSTRUCTION OF PUERTO PRINCESA
SUPER HEALTH CENTER
154 |  | MAT (MEALS, ACCOMMODATION AND |  | Puerto Princesa City | 3741500 |  | 2022-05-12 | 2022-12-31 |  | 100 | 3741500 | 0
TRANSPORTATION) - HCWS
155 |  | LOTTO FUND UTILIZATION REPORT |  | Puerto Princesa City | 5009389.33 |  | 2021-11-02 | 2026-12-31 |  | 0 | 0 | 0
156 |  | STL FUND UTILIZATION REPORT |  | Puerto Princesa City | 958191.04 |  | 2021-07-12 | 2026-12-31 |  | 0 | 0 | 0
157 |  | TRANSFER OF FUND FOR PUERTO PRINCESA |  | Bgy. Irawan, PPC | 1000000 |  | 2024-01-11 | 2023-12-31 |  | 0 | 0 | 0 | Refunded to DOH last November 2025
CITY MOLECULAR DIAGNOSTIC LABORATORY
158 |  | HEALTH EMERGENCY ALLOWANCE (HEA) - JULY |  | Puerto Princesa City | 9444250 |  | 2023-07-21 | 2023-12-31 |  | 100 | 9444250 | 0
2021
159 |  | HEALTH EMERGENCY ALLOWANCE (HEA) - AUGUST |  | Puerto Princesa City | 9660875 |  | 2023-07-21 | 2023-12-31 |  | 100 | 9660875 | 0
2021
160 |  | HEALTH EMERGENCY ALLOWANCE (HEA) - |  | Puerto Princesa City | 10054437.5 |  | 2023-07-21 | 2023-12-31 |  | 100 | 10054437.5 | 0
SEPTEMBER 2021
161 |  | HEALTH EMERGENCY ALLOWANCE (HEA) - |  | Puerto Princesa City | 10274562.5 |  | 2023-07-21 | 2023-12-31 |  | 100 | 10274562.5 | 0
OCTOBER 2021
162 |  | HEALTH EMERGENCY ALLOWANCE (HEA) - |  | Puerto Princesa City | 10438312.5 |  | 2023-07-21 | 2023-12-31 |  | 100 | 10438312.5 | 0
NOVEMBER 2021
163 |  | HEALTH EMERGENCY ALLOWANCE (HEA) - |  | Puerto Princesa City | 10368437.5 |  | 2023-07-21 | 2023-12-31 |  | 100 | 10368437.5 | 0
DECEMBER 2021
164 |  | HC- MANGINGISDA SATELLITE CLINIC AND |  | Bgy. Mangingisda, PPC | 462877.5 |  | 2023-06-13 | 2026-12-31 |  | 22.5546 | 104400 | 0
BIRTHING FACILITY
165 |  | PF- MANGINGISDA SATELLITE CLINIC AND |  | Bgy. Mangingisda, PPC | 130786 |  | 2023-06-13 | 2025-12-31 |  | 47.0998 | 61600 | 0
BIRTHING FACILITY
166 |  | HC- SAN RAFAEL SATELLITE CLINIC AND |  | Bgy. San Rafael, PPC | 403766 |  | 2023-06-13 | 2025-12-31 |  | 15.9274 | 59550 | 0
BIRTHING FACILITY
167 |  | PF- SAN RAFAEL SATELLITE CLINIC AND |  | Bgy. San Rafael, PPC | 61858 |  | 2023-06-13 | 2025-12-31 |  | 59.3294 | 36700 | 0
BIRTHING FACILITY
168 |  | HC- CABAYUGAN SATELLITE CLINIC AND |  | Bgy. Cabayugan, PPC | 18900 |  | 2023-06-13 | 2025-12-31 |  | 100 | 18900 | 0
BIRTHING FACILITY
169 |  | PF- CABAYUGAN SATELLITE CLINIC AND |  | Bgy. Cabayugan, PPC | 10600 |  | 2023-06-13 | 2025-12-31 |  | 100 | 10600 | 0
BIRTHING FACILITY
170 |  | HC- SALVACION SATELLITE CLINIC AND |  | Bgy. Salvacion, PPC | 39840 |  | 2023-06-13 | 2025-12-31 |  | 11.8725 | 4730 | 0
BIRTHING FACILITY
171 |  | PF- SALVACION SATELLITE CLINIC AND |  | Bgy. Salvacion, PPC | 3200 |  | 2023-06-13 | 2025-12-31 |  | 100 | 3200 | 0
BIRTHING FACILITY
172 |  | SOCIAL PENSION PROGRAM - 1ST & 2ND |  | Puerto Princesa City | 38235000 |  | 2023-06-26 | 2023-12-31 |  | 100 | 38235000 | 0
QUARTER 2023
173 |  | SOCIAL PENSION PROGRAM - 3rd & 4th |  | Puerto Princesa City | 38235000 |  | 2023-12-05 | 2023-12-31 |  | 100% | 38235000
QUARTER 2023
174 |  | DOH FIXED TRANCHE 2023 |  | Puerto Princesa City | 1724930.99 |  | 2023-07-21 | 2023-12-31 |  | 100 | 1724930.99 | 0
175 |  | LGSF-ELCAC BATCH 1 - CONCRETING OF FARM-TO |  | Bgy. Marufinas, Bgy. New Panggangan, & Tagabinit, PPC | 19820646.48 |  | 2023-06-21 | 2023-12-31 |  | 100 | 19820646.48 | 0
-MARKET ROAD AT BGY. MARUFINAS, SOLAR
ELECTRIFICATION AT BGY. NEW PANGGANGAN,
AND REHABILITATION OF FARM-TO-MARKET
ROAD AT BGY.TAGABINIT
176 |  | LOCAL GOVERNMENT SUPPORT-FUND - FINANCIAL ASSISTANCE TO LGUs, FY 2024 GAA, RA NO. 11975/ Assistance to Indigent Individuals or Families: Food Assistance |  |  | 3000000 |  | 2024-07-08 | 2024-07-31 |  | 100% | 3000000
177 |  | 20% LGU SHARE IN FIRE CODE FEES COLLECTED |  | Puerto Princesa City | 6304426.81 |  | 2023-08-04 | 2025-12-31 |  | 99.9021 | 6298256 | 0
FOR FY 2018, 2020 and 2021
178 |  | PHILHEALTH KONSULTA |  | Puerto Princesa City | 58099.09 |  | 2023-07-27 | 2023-12-31 |  | 0 | 0 | 0
179 |  | 2023 HEALTHY PILIPINAS AWARDING |  | Puerto Princesa City | 150000 |  | 2024-02-22 | 2024-03-31 |  | 100 | 150000 | 0
180 |  | PUERTO PRINCESA CITY TOURISM TRUST FUND |  | Puerto Princesa City | 8058.24 |  | 2022-08-15 | 2024-12-31 |  | 0 | 0 | 0
181 |  | DISASTER RESPONSE AND EARLY RECOVERY FOR THE FIRE VICTIMS FROM BGY PAGKAKAISA & BAGONG SILANG |  | Puerto Princesa City | 131000000 |  | 2024-02-14 | 2024-12-31 |  | 60.7198 | 79542991.09 | 0
182 |  | HEALTH EMERGENCY ALLOWANCE - JULY 2022 |  | Puerto Princesa City | 8351687.5 |  | 2024-04-02 | 2024-12-31 |  | 100% | 8351687.5 | 0
183 |  | HEALTH EMERGENCY ALLOWANCE - AUGUST 2022 |  | Puerto Princesa City | 8424000 |  | 2024-04-02 | 2024-12-31 |  | 100% | 8424000 | 0
184 |  | HEALTH EMERGENCY ALLOWANCE - SEPTEMBER 2022 |  | Puerto Princesa City | 8400937.5 |  | 2024-04-02 | 2024-12-31 |  | 100% | 8400937.5 | 0
185 |  | HEALTH EMERGENCY ALLOWANCE - OCTOBER 2022 |  | Puerto Princesa City | 8355500 |  | 2024-04-02 | 2024-12-31 |  | 100% | 8355500 | 0
186 |  | HEALTH EMERGENCY ALLOWANCE - NOVEMBER 2022 |  | Puerto Princesa City | 8397062.5 |  | 2024-04-02 | 2024-12-31 |  | 100% | 8397062.5 | 0
187 |  | HEALTH EMERGENCY ALLOWANCE - DECEMBER 2022 |  | Puerto Princesa City | 8256656.25 |  | 2024-04-02 | 2024-12-31 |  | 100% | 8256656.25 | 0
188 |  | Preliminary Disinfection and Storage Facility (PDSF) |  | So. Magarwak, Barangay Sta. Lourdes, Puerto Princesa City | 121000 |  | 2023-12-01 | 2024-12-31 |  | 0% | 0 | 0
189 |  | Construction of RC Box Culvert at Old Santol Road |  | Old Santol Road, Barangay San Jose, Puerto Princesa City | 5316000 |  | 2024-02-14 | 2024-12-31 |  | 100% | 5236935.93 | 0
190 |  | Construction of Drainage System from Napocor Road to San Manuel Sea Road II |  | Napocor Road to San Manuel Sea Road II, Barangay San Manuel, Puerto Princesa City | 18638076 |  | 2024-02-14 | 2024-12-31 |  | 100 | 18606482.2 | 0
191 |  | DOH FIXED TRANCHE 2024 |  | Puerto Princesa City | 5663392.86 |  | 2024-08-15 | 2025-06-30 |  | 100 | 5663392.86 | 0
192 |  | 2024 HEALTHY SETTINGS PROGRAM |  | Puerto Princesa City | 3800000 |  | 2024-08-15 | 2025-09-30 |  | 85.3247 | 3242338.74 | 0
193 |  | PHILHEALTH KONSULTA 2024 (TO 2026) |  | Puerto Princesa City | 56051450.11 |  | 2024-08-07 | 2026-12-31 |  | 48.9475 | 27435787.59 | 0
194 |  | HEALTH EMERGENCY ALLOWANCE - JANUARY 2023 |  | Puerto Princesa City | 4334250 |  | 2024-09-03 | 2024-12-31 |  | 100% | 4334250 | 0
.
195 |  | HEALTH EMERGENCY ALLOWANCE - FEBRUARY 2023 |  | Puerto Princesa City | 4352781.25 |  | 2024-09-03 | 2024-12-31 |  | 100% | 4352781.25 | 0
196 |  | HEALTH EMERGENCY ALLOWANCE - MARCH 2023 |  | Puerto Princesa City | 4397250 |  | 2024-09-03 | 2024-12-31 |  | 100% | 4397250 | 0
197 |  | HEALTH EMERGENCY ALLOWANCE - APRIL 2023 |  | Puerto Princesa City | 4217562.5 |  | 2024-09-03 | 2024-12-31 |  | 100% | 4217562.5 | 0
198 |  | HEALTH EMERGENCY ALLOWANCE - MAY 2023 |  | Puerto Princesa City | 4446312.5 |  | 2024-09-03 | 2024-12-31 |  | 100% | 4446312.5 | 0
199 |  | HEALTH EMERGENCY ALLOWANCE - JUNE 2023 |  | Puerto Princesa City | 4381406.25 |  | 2024-09-03 | 2024-12-31 |  | 100% | 4381406.25 | 0
200 |  | HEALTH EMERGENCY ALLOWANCE - JULY 2023 |  | Puerto Princesa City | 4095437.5 |  | 2024-09-03 | 2024-12-31 |  | 100% | 4095437.5 | 0
201 |  | SOCIAL PENSION FOR INDIGENT SENIOR CITIZENS IN DIFFERENT BARANGAYS IN PUERTO PRINCESA |  | Barangay San Miguel, Puerto Princesa City | 43284000 |  | 2024-11-06 | 2024-12-31 |  | 100% | 43284000 | 0
202 |  | FINANCIAL ASSISTANCE TO LGUS AFFECTED FAMILIES OF COMBINED EFFECTS OF THE ENHANCED SOUTHWEST MONSOON AND TROPICAL CYCLONE FERDIE, GENER, HELEN, AND IGME LAST SEPTEMBER 11 TO SEPTEMBER 22, 2024 |  | Puerto Princesa City | 250000 |  | 2024-12-19 | 2024-12-31 |  | 0% | 0 | 0
203 |  | PRESIDENTIAL ASSISTANCE FOR FARMERS, FISHERFOLKS, AND OTHER FAMILIES AFFECTED BY EL NIÑO |  | Puerto Princesa City | 10000000 |  | 2024-11-11 | 2024-12-31 |  | 100% | 10000000 | 0
204 |  | BATANG PINOY NATIONAL CHAMPIONSHIPS 2024 |  | Puerto Princesa City | 4000000 |  | 2024-11-26 | 2024-12-31 |  | 100% | 3951100 | 0
205 |  | MICE 101 & 102 Training Programs |  | Puerto Princesa City | 1259433 |  | 2024-11-22 | 2024-12-31 |  | 100% | 1259433 | 0
206 |  | INTENSIVE ASSESSMENT AND DOCUMENTATION OF THE CAVES AND KARSTS COMPLEX OF PPSRNP |  | Puerto Princesa City | 1850000 |  | 2024-10-03 | 2024-12-31 |  | 100 | 1850000 | 0
207 |  | 2024 IP HEALTH PROJECT |  | Puerto Princesa City | 750000 |  | 2024-12-12 | 2025-03-31 |  | 100% | 750000 | 1
208 |  | MEASLES RUBELLA AND ORAL POLIO VACCINE SUPPLEMENTAL IMMUNIZATION ACTIVITY 2024 |  | Puerto Princesa City | 160000 |  | 2024-11-04 | 2024-12-31 |  | 24.8% | 160000 | 0 | 75.2% unutilized refunded to DOH
209 |  | Construction of Drainage System from Caimito Road I to North National Highway |  | Puerto Princesa City | 18397365 |  | - | 2024-12-31 |  | 0% | 0 | 0
210 |  | Assistance to Individuals and Families in Crisis Situation (AICS) 2025 |  | Puerto Princesa City | 15000000 |  | 2025-03-24 | 2025-03-27 |  | 100% | 15000000 | 0
211 |  | Puerto Princesa City Environmental Forum 2025 |  | Puerto Princesa City | 103666.31 |  | 2025-02-24 | 2025-02-25 |  | 70.8938 | 73493 | 0 | Reprogrammed funds from IGES
212 |  | Establishment of Specimen Storage Room |  | Puerto Princesa City | 3637352.3 |  | - | 2025-12-31 |  | 35.05% | 1274990.19 | 0
213 |  | 20% Fire Code Fees in FY 2014, 2015 and 2022 |  | Puerto Princesa City | 3591175.43 |  | 2025-05-29 | 2025-12-31 |  | 48.9603 | 1758250.13 | 0
214 |  | Social Pension Program for Indigent Senior Citizens in Different Barangays of Puerto Princesa City (2025) |  | Puerto Princesa City | 113481000 |  | 2025-05-14 | 2025-12-31 |  | 100 | 113481000 | 0
215 |  | Establishment of Permanent Evacuation Center Project |  | Puerto Princesa City | 50000000 |  | - | 2024-12-31 |  | 0% | 0 | 0
216 |  | 7 Units of 70HP Submersible Pump With Trailer, Power Supply and Accessories |  | Puerto Princesa City | 19600000 |  | 2025-09-11 | 2025-12-31 |  | 100 | 19598000 | 0
217 |  | 21 Pcs 24 to 25 Meter 200 mm. hose (PVC or Flexible Hose) |  | Puerto Princesa City | 1470000 |  | 2025-09-11 | 2025-12-31 |  | 100 | 1465000 | 0
218 |  | 4 Units Backhoe |  | Puerto Princesa City | 8400000 |  | 2025-09-11 | 2025-12-31 |  | 0% | 0 | 0
219 |  | Renovation of CDRRMC Main Warehouse |  | Puerto Princesa City | 3000000 |  | 2024-11-24 | 2025-12-31 |  | 100% | 2931826.94 | 0
220 |  | Construction of a Flood Control Project from Peneyra Road, Barangay San Pedro |  | Bgy. San Pedro, PPC | 32000000 |  | Within 2026 | 2025-12-31 |  | 1.99% | 636115.6826 | 0
221 |  | 2025 LHSDA Grants |  | Puerto Princesa City | 6084189.39 |  | 2025-08-28 | 2026-03-31 |  | 90.8439 | 5527112.14 | 0
222 |  | HCI - Animal Bite Treatment Center (ABTC) |  | Puerto Princesa City | 1616100 |  | 2025-05-23 | 2026-12-31 |  | 0% | 0 | 0
223 |  | HCI - TB DOTS |  | Puerto Princesa City | 1062100 |  | 2025-05-23 | 2026-12-31 |  | 50.2755 | 533975.83 | 0
224 |  | PF - Macarascas Satellite Clinic and Birthing Facility |  | Puerto Princesa City | 173550 |  | 2025-07-22 | 2026-12-31 |  | 0% | 0 | 0
225 |  | 20% Fire Code Fees in FY 2015, 2016 and 2023 |  | Puerto Princesa City | 5167106.68 |  | 2025-07-17 | 2026-12-31 |  | 0% | 0 | 0
226 | 2025 Healthy Settings Program |  |  | Puerto Princesa City | 5000000 |  | 2025-12-11 | 2026-05-31 |  | 87.9179 | 4395896.5 | 1
227 |  | HEA July 2021 to July 2023 Appeal |  | Puerto Princesa City | 17980500 |  | 2025-12-26 | 2026-02-28 |  | 100 | 16877000 | 0 | Remaining balance already in process for refund to DOH
228 |  | PF- STA. MONICA SATELLITE CLINIC AND BIRTHING FACILITY |  | Barangay Sta. Monica, Puerto Princesa City | 26520 |  | 2025-09-24 | 2026-12-31 |  | 0% | 0 | 0
229 |  | Supplies for Temporary Repair of Damaged Water Connection in Brgy. New Panggangan |  | Barangay New Panggangan, Puerto Princesa City | 728665.2 |  | 2026-06-29 | 2026-12-31 |  | 99.9993 | 728660 | 0
Barangay New Panggangan, Puerto Princesa City
230 |  | Construction and Rehabilitation of Barangay Water Supply System in Brgy. New Panggangan |  | Barangay New Panggangan, Puerto Princesa City | 8500000 |  | - | 2026-12-31 |  | 0% | 0 | 0
231 |  | Local Government Support Fund - Financial Assistance to LGUs, FY 2026 GAA, RA No. 12314: Assistance to Indigent Individuals or Families - Food Assistance/Rice Distribution Project |  | Puerto Princesa City | 48000000 |  | 2026-03-30 | 2026-12-31 |  | 16.5833 | 7960000 | 0
232 |  | Local Government Support Fund - SBDP of the NTF to ELCAC, FY 2026 GAA, RA No. 12314: Concreting of Farm-to-Market Road at Bgy. Cabayugan |  | Barangay Cabayugan, Puerto Princesa City | 10000000 |  | 2026-03-26 | 2026-12-31 |  | 0% | 0 | 0
233 |  | Local Government Support Fund - SBDP of the NTF to ELCAC, FY 2026 GAA, RA No. 12314: Concreting of Farm-to-Market Road at Bgy. Inagawan |  | Barangay Inagawan, Puerto Princesa City | 10000000 |  | 2026-03-26 | 2026-12-31 |  | 0% | 0 | 0
234 |  | Local Government Support Fund - SBDP of the NTF to ELCAC, FY 2026 GAA, RA No. 12314: Construction of Level II Potable Water Supply System at Bgy. Langogan |  | Barangay Langogan, Puerto Princesa City | 10000000 |  | 2026-03-26 | 2026-12-31 |  | 0.0129 | 1290 | 0
235 |  | Local Government Support Fund - SBDP of the NTF to ELCAC, FY 2026 GAA, RA No. 12314: Concreting of Farm-to-Market Road at Bgy. Lucbuan |  | Barangay Lucbuan, Puerto Princesa City | 10000000 |  | 2026-03-26 | 2026-12-31 |  | 0% | 0 | 0
236 |  | Local Government Support Fund - SBDP of the NTF to ELCAC, FY 2026 GAA, RA No. 12314: Concreting of Farm-to-Market Road at Bgy. Tagburos |  | Barangay Tagburos, Puerto Princesa City | 10000000 |  | 2026-03-26 | 2026-12-31 |  | 0% | 0 | 0
237 |  | Implementation of Purok Kalusugan and IP Health Project 2026 |  | Puerto Princesa City | 1000000 |  | 2026-05-19 | 2026-12-31 |  | 0% | 0 | 0
238 |  | 2025 Rafael M. Salas Kaunlarang Pantao Award ( RMSKPA) 2nd place winner for the City Category |  | Puerto Princesa City | 200000 |  | 2026-04-06 | 2026-12-31 |  | 0% | 0 | 0
239 |  | Social Pension Program for IP SCs of PPC - 3rd Quarter 2026 |  | Puerto Princesa City | 33150000 |  | 2026-03-26 | 2026-09-30 |  | 100% | 31836000 | 0 | Remaining balance already in process for refund to DSWD
240 |  | HC - Macarascas Satellite Clinic and Birthing Facility |  | Puerto Princesa City | 49140 |  | 2026-05-26 | 2026-12-31 |  | 0% | 0 | 0
241 |  | HC- STA. MONICA SATELLITE CLINIC AND BIRTHING FACILITY |  | Puerto Princesa City | 27480 |  | 2026-04-07 | 2026-12-31 |  | 0% | 0 | 0
242 |  | 20% Fire Code Fees in FY 2017, 2019 and 2024 |  | Puerto Princesa City | 6656743.32 |  | 2026-08-06 | 2027-12-31 |  | 0% | 0 | 0
| TOTAL |  |  |  | 2237005485.55 | [5 empty] | 1898360836.6726
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
CHARLITO B. PADUL | [5 empty] | LUCILO R. BAYRON
City Accountant | [5 empty] | Local Chief Executive
Note on U474: ELLA: UPDATED
Note on H544: including adjustments